## 2026
Job # | Builder | Client's Name | Address | Description of work | Est. Duration | Ttl SF/LF | Approximate Start Date | Project Manager | Pre-Lien Req'd | Job status
26001 | Clearstone | Bowman |  | Veneer |  |  | February | Clint/Dennis
26002 | Chamberlain | Whitby |  | Paving | 1 month |  | February | Dennis
26003 | Killowen | Smith |  | Veneer | 3 months | 5000 |  | Chris
26004 | Olson | Judy Olson |  | Paving | 1 week | 500 |  | Dennis
26005 | Biltmore | Mitt Romney |  | Veneer | 1 week
26006 | Jackson Leroy | Kappas |  | Veneer | 3 months | 4500 | Summer | Chris
26007 | Chamberlain | Verhaaren
26008 | Sunline | Rich Wood |  | Caps repair
26009 | Kent | Eller |  | Veneer | 3 months | 4500 | Summer/Fall | Chris
26010 | Kent | Quinnild |  | Veneer | 2 months | 3500 | May | Chris
26011 | Vitruvius | Green |  | Veneer | 3 months | 5500 | May | Chris
26012 | JAL Pools | Thompson |  | Coping repair | 2 days | 40 | Mid March | Jose
26013 | Luxus Design Build |  |  | supply |  |  | February | Darin
26014 | Aspen Lane Homes | Jimenez |  | FP and Entry | 1 week |  | April | Dennis/Manolo
26015 | United Contractors | Colton |  | Entry | 3 days |  | May | Dennis/Manolo
26016 | Kappus | Colony 216 |  | landscaping | 1 month | 1700 | Summer | Chris
26017 | Kent | Benkendorf |  | paving | 1 month | 1800 | May | Chris
26018 | Global Stone/Jacobsen | Cormont Bldg 1 |  | Veneer | 2 montsh | 4850 | June/July | Chris
26019 | Build UT | Johnson |  | FP, FB and repairs | 3 weeks |  | May | Dennis
26020 | Build UT | Berman Belle |  | Veneer | 3 months | 6000 | August | Chris
26021 | Alpenglow | Grizzly Gulch |  | Veneer | 2 months | 3000 | June | Dennis/Clint
26022 | Aspen Pools | Laub |  | Paving | 1 montsh | 3200 | May/June | Chris/Jose
26023 | Jackson Leroy | Olson |  | Veneer
26024 | Sunline | Sorensen |  | Firepit | 1 week |  | April/May | Dennis
26025
26026
26027
26028
26029
26030
26031
26032
26033
26034
26035

## 2025
Job # | Builder | Client's Name | Address | Description of work | Est. Duration | Ttl SF/LF | Approximate Start Date | Project Manager | Pre-Lien Req'd | Job status
25001 | Magleby Construction | Marshall |  | Veneer/Hardscape | 1 year | 20000 | April | Chris | Yes
25002 | Brad Reynolds | Reynolds |  | copings, pavings | 2 months | 1500 | April | Dennis/Jose
25003 | Biltmore | Moore |  | Veneer | 2 months | 3000 | February | Dennis
25004 | JAL Pools | Ryan Smith |  | pool copings | 2 weeks |  | April | Dennis/Jose
25005 | Tempest Design | Lane Critchfield |  | Fireplace | 2 days |  | March | Dennis/Manolo
25006 | Jackson Leroy | Hyde |  | Veneer | 3 days | 30 | February | Dennis
25007 | Groove Homes | Crow Creek |  | Fireplace | 1 day |  | March | Chris
25008 | Kappus | McGuire |  | copings, pavings | 2 months | 1700 | March | Dennis
25009 | Kappus | H Taylor Sommer Hill |  | paving | 1 week | 400 | February | Dennis/jose
25010 | Jackson Leroy | Peterson Gate |  | CMU/Stone | 2 weeks | 500 | February | Dennis/Clint
25011 | Sunline | Mustard |  | paving | 2 months | 8000 | April | Dennis/Jose
25012 | Sunline | Keystone; Paving |  | Paving | 2 months | 6000 | April | Dennis/jose
25013 | McEwan Homes | Keystone, Entry |  | CMU/Stone walls | 3 montsh | 20000 | March | Dennis
25014 | AMB | Freedman |  | Fireplaces | 2 weeks |  |  | Chris
25015 | Clearstone | Nemelka |  | Veneer | 3 months | 8000 |  | Dennis
25016 | Jackson Leroy | Tim Fenton |  | hardscaping | 2 months |  |  | Dennis/CLint
25017 | Ethos | Jeremy Jackson |  | bluestone paving | 3 days |  |  | Dennis/jose
25018 | Jackson Leroy | Hopkins Carriage House |  | Veneer and paving | 1 month |  | May | Dennis/Clint
25019 | Magleby Construction | River Bend |  | Veneer | 1 month | 1400 | May | Chris
25020 | Brinkerhoff | Brinkerhoff (Mary/Alan) |  | Veneer | 2 months |  | April | Dennis
25021 | Robinson Builders | Ali Henrie |  | hearth | 1 day |  |  | Clint
25022 | Chamberlain | Marquardt |  | Repairs | 3 days |  | April | Clint
25023 | Magleby Construction | Colony 253 |  | Wall caps | 3 days | 70 | May | Chris
25024 | JacksonLeroy | Hyde |  | T&M | 1 week | 100 | May | Dennis/Clint
25025 | Sunline | Belcher |  | hardscaping | 2 weeks |  | June | Dennis
25026 | JacksonLeroy | Doran Taylor |  | Veneer |  |  | June | Dennis
25027 | Magleby Construction | Dickson Cabin |  | Veneer | 2 months | 5000 |  | Chris
25028 | JAL Pools | Kirkham |  | Copings | 1 week |  | June | Chris
25029 | Kappus | Lowe |  | hardscaping | 3 weeks |  | July | Dennis
25030 | Jackson leroy | Bowman |  | Repairs | 1 week |  | May | Chris
25031 | Jackson Leroy | Bar J |  | Veneer | 6 months |  |  | Dennis
25032 | Jackson Leroy | Ostler |  | pool copings | 1 day |  | June | Dennis
25033 | Brad Reynolds | Foote |  | veneer | 2 weeks | 600 | June | Dennis
25034 | JAL Pools | Lane Myers
25035 | Omega Pools | Berg |  | copings, pavings | 2 weeks |  | May | Chris/Clint
25036 | JAL Pools | Cris Carter |  | coping repairs | 1 day |  | June | Chris
25037 | Kappus | Vandernakk |  | paving/coping | 1 month |  | Sept | Dennis/jose
25038 | Magleby Construction | Sorensen Pavilion |  | Veneer and paving | 3 months | 5000 |  | Dennis
25039 | Kappus | Hagen |  | paving/coping | 2 weeks | 700 | July | Dennis/Jose
25040 | Omega Pools | Gould |  | copings | 2 weeks |  | July | Chris/Clint
25041 | Ingerson Const. | Paddleboard |  | fireplaces | 3 days |  | July | Chris
25042 | Kent Const | Woodruff |  | Veneer | 3 months | 6500 | November | Chris
25043 | Kent Const | Herman |  | Veneer | 3 months | 6000 | December | Chris
25044 | Kappus | Kelly |  | caps | 3-4 days |  |  | Dennis/jose
25045 | Kappus | Eliz Taylor |  | hardscaping | 2 months |  | Sept | Dennis
25046 | JAL Pools | Strike |  | coping | 3 days |  | Sept | Dennis/jose
25047 | Jackson Leroy | Maxfield |  | Architectural surroun | 1 week |  | November | Dennis/Manolo
25048 | J Christoper GC | Southwick |  | veneer | 1 month |  | October | Dennis
25049 | Jackson Leroy | Matt Fenton |  | Paving repairs | 1 month |  | September | Dennis/Clint
25050 | Homeowner (no contractor) | James Gee |  | Paving repairs | 1 day |  | September | Dennis
25051 | Jackson Leroy | Ostler River House |  | Paving repairs | 3 days |  | September | Chris
25052 | Build Utah/Russell | Meehan Barnes |  | fireplace | 1 day |  | September | Dennis
25053 | Jackson Leroy | Jeremy Jackson |  | paving | 3 days |  | October | Dennis
25054 | Jackson Leroy | Colony 206 |  | veneer/coping | 2 weeks | 350 | October | Chris
25055 | Jackson Leroy | Enenstein
25056 | Kappus | Brinkerhoff |  | thresholds | 1 day | 25 | October | Dennis/Jose
25057 | RA Ferrin | Vintage Cove |  | Repairs | 2 days |  | November | Chris
25058 | Heritage Homes | Mustard Mantles |  | fireplaces | 1 week |  | October | Dennis/Manolo
25059 | Brandon Bodell | Heidi Brewer |  | veneer | 2 months |  | November | Dennis
25060 | Killowen | Ryland |  | Veneer | 2 months | 4500 | Spring 26
25061 | Brandon Bodell | Ross |  | Fireplaces & FB | 1 week |  |  | Dennis/Manolo
25062 | Magleby Construction | Lisonbee Barn |  | fireplace | 1 week | 470 | November | Chris
25063 | Brandon Bodell | Thurston |  | Veneer | 2 months | 4000 | December | Chris
25064 | Brandon Bodell | Meachm |  | Veneer | 3 months | 7000 | December | Dennis
25065 | Fazzino | Fazzino |  | Mailbox | 3 days |  | December | Dennis
25066 | Complete Contracting | Holladay Hills 501 |  | fireplace | 1 day |  | December | Dennis/Manolo
25067 | Biltmore | Brimley |  | fireplace | 1 day |  | December | Dennis/Manolo
25068 | Night Vision | Gilbert |  | Veneer | 1 day |  | January | Dennis

## 2023
Job # | Builder | Client's Name | Address | Description of work | Est. Duration | Ttl SF/LF | Approximate Start Date | Project Manager | Pre-Lien Req'd | Job status
23001 | Bill Jacoby-Vallone Design | Bill Jacoby | 2645 Talon Way, Park City | 2 Fireplaces | 3 weeks | 450 | 2023-01-23 | Chris
23002 | Tuck Landscaping | Teerlink | 1947 E Michigan Ave, SLC | landscaping | 6 weeks | 1500 |  | Dennis
23003 | JAL Pools | Rasmussen | 3131 Cottonwood Lane, Provo | Pool coping/veneer | 3 weeks |  | April | Darin
23004 | Watts Enterprises | England | 3960 Nordic Valley Drive, Eden | Veneer | 6 months | 10000 | January | Darin-Bryce Warren | yes | started
23005 | Magleby Construction | Aspen Camp 84 | 7834 N Moon Dog, Park City | Veneer | 3 months | 5000 | April | Chris | yes
23006 | Sunline Landscapes | Urrechanga | Park City | Kitchen veneer | 3 days | 300 | April | Chris
23007 | Smith Setjo | Parsons | 1719 Millcreek Way, Holladay | fireplace | 1 day |  | Feb | Dennis
23008 | Russel & Co | Pierce | Lot 304, 6795 N Moonrise Way, Kamas | Veneer | 2 months | 4600 | Feb | Chris | yes
23009 | Magleby Construction | Magleby Masterpiece | Geneva Road | Veneer | 1 weeks | 200 | Feb | Dennis & Juan | no
23010 | Kent Construction | Sweetman | 9353 Promontory Summit Drive | Veneer | 3 months | 9000 | Feb | Chris | yes
23011 | Doug Knight | Parker | 7590 Bugle Trail, Promontory | Fireplaces | 2 weeks |  | Feb | Chris
23012 | Jackson Leroy | Broeberg | 1095 Quail Summit Dr, Provo | Brick repair | 2 weeks | 200 | Feb | Dennis |  | Started
23013 | Omega Pools |  |  | pool coping | 1 week |  | Feb | Chris |  | started
23014 | JAL Pools | Bray | 2083 Walker Lane | pool coping | 1 week |  | July | Jose
23015 | Jackson Leroy | Hyde | Wasatch Peak Lot E5, Peterson UT | paving | 2 months | 4000 | Fall | Dennis & Bryce
23016 | Jackson Leroy | Smith | 1780 E Siesta Drive, Cottonwood Heights | Veneer | 4 months | 10000 | May | Dennis & Troy
23017 | Jackson Leroy | Archibald Estate | 1777 West Midway Lane, Midway | Veneer | 2 months | 3000 | July | Chris
23018 | Paragon Custom Builders | Schwebach | 1792 S Sunset Point Circle, Kaysville | Fireplaces | 2 days |  | May | Darin-Dennis
23019 | Kent Construction | Queen | 6515 E Mayfly Court, Heber | Veneer | 3 months | 5500 |  | Chris
23020 | Jackson Leroy | Wirthlin Mailbox | Salt Lake | Mailbox | 2 days |  | April | Dennis & Juan
23021 | Rob Mcarthur | Laub | 1066 Canyon Road, Logan | statues | 1 day |  | May | Darin
23022 | Chamberlain Homes | Cooley | 2344 East Olympus Drive, Holladay | pool coping | 3 weeks |  | June | Dennis & Juan
23023 | Cedar Valley Construction | Belwin | 7226 N Bugle Trail, Promontory | Veneer | 2 months | 4200 | June | Chris
23024 | Dal Hills | Hills | 480 South 250 West, Midway | pool coping | 2 days |  |  | Darin
23025 | Dolphin Pools | Raybould | 2640 E Rowland Dr, SLC 84124 | pool coping | 3 days |  | May | Dennis
23026 | JAL Pools | Clack | 28597 Parleys Lane, Park City | pool coping | 1 week | 200 |  | Chris
23027 | Jackson Leroy | Wennerth | 2676 Meadow Creek Dr. PC | repairs | 3 days |  | May | Chris
23028 | Jackson Leroy | Bethany Sorensen | 601 South Pheasant Ridge Cr, Alpine | Veneer | 2 months | 2500 | June | Dennis
23029 | Jackson Leroy | Wheeler | 7589 N Bugle Trails, Promontory | Veneer | 6 months | 7500 | July | Chris
23030 | Jackson Leroy | Grigg | 2090 E FLat Top Mountain Drive, Heber | repairs | 2 days |  |  | Chris
23031 | Magleby Construction | Slobodow | 3189 American Sadler, Park City | repairs | 2 days |  | July | Chris
23032 | Kent Construction | VR 187 | 7225 North Constellation Court, Victory Ranch | paving | 3 days | 325 | June | Chris
23033 | Collett Brothers | Collett | Kaysville | Veneer | 3 months | 5000 | July | Bryce
23034 | Jackson Leroy | Crocker | 3764 Thousand Oaks Circle, SLC | fireplaces | 1 week |  | August | Dennis
23035 | Jackson Leroy | Heiden | 1219 Cottonwood Lane, Park City | Paving & firepits | 3 weeks | 1100 | August | Chris
23036 | Jackson Leroy | Faux | 4346 Vintage Drive, Provo | Fireplace1 | 2 days |  |  | Darin
23037 | Jackson Leroy | Hagen | 4274 North Sheffield Dr. Provo | FP & remodel | 1 month | 1500 | October | Dennis
23038 | Kappus | Morris | 2905 Connor Street, Millcreek | landscaping | 1 week | 200 | September | Dennis
23039 | Paragon Custom Builders | Zimmermann | 1783 E Millbrook Rd, Millcreek | fireplace | 1 day
23040 | Brandon Bodell | Kringlen | 1020 Plum Tree Court, North Salt Lake | Trims | 1 week |  | September | Darin-Dennis
23041 | Magleby Construction | Jenson | Colony 319, Park City | Veneer | 1 year | 16000 |  | Chris
23042 | Kappus | Barney | 1892 E Olympus Grove Lane, Holladay | Paving & FP | 2 weeks |  |  | Dennis
23043 | Kappus | Wilmarth | 4944 S Marilyn Drive, Holladay | Paving | 4 weeks |  |  | Dennis
23044 | Goldthorpe | Luttrell | 6304 S 1125 E, Murray | Veneer | 9 months | 14000 | February | Dennis & Juan
23045 | Magleby Construction | Chad Magleby | 427 East 70 North, Lindon | Paving & Veneer | 2 days |  | September | Dennis
23046 | Jackson Leroy | DeGeorge | 320 N 6900 E, Huntsville | Paving | 1 mond | 4500 | October | Bryce
23047 | Jackson & Leroy | McCuen | 2393 N Hwy 40, Heber | repairs | 2 days |  | September | Chris
23048 | Grove Homes | Bodily | 165 W Creekside, Alpine | 2 fireplaces | 3 days |  | September | Dennis
23049 | Cedar Valley Homes | Woodley | 250 N Trappers Loop Rd. HEber; Wolf Creek | Veneer | 9 months |  | May | Chris
23050 | Art Turner | Turner | 2412 E Oakcrest Lane, SLC | fireplace | 1 day |  | October | Dennis
23051 | Noorda | Chris Noorda | 13712 South Fort Steet, Draper | fireplace | 1 day |  | September | Dennis
23052 | Paragon Custom Builders | RJ Gardner | 6259 W 9960 N, Highland | hearth | 1 day |  | October | Dennis
23053 | JAL Pools | Danny Ainge | 1274 South 1100 East, Berkshires Orem | pool coping | 1 week |  | October | Dennis
23054 | Jackson Leroy | Robertson | 9810 E Martha Road, Sandy | repairs | 2 days |  | October | Dennis
23055 | Jackson Leroy | Rochelle Warner | 1804 Millbrook Road, SLC | repairs | 3 days |  | October | Dennis & Juan
23056 | Jason Boyer | Boyer | 617 E Zachary Way, Alpine | fireplace | 2 days |  | November | Dennis
23057 | Jackson Leroy | Jeremy Jackson | SLC | paving |  |  |  | Dennis & Juan
23058 | Chad Christensen | Christensen | SLC | Fireplace | 1 week |  | December | Dennis
23059 | Norman | O'Connel | 2520 E Sundowner Ridge Dr. Kamas | Hearth | 2 hours |  | November | Chris
23060 | Grove Homes | Nelson | 374 W 500 S, Midway | Fireplaces | 1 week |  | November | Chris
23061 | Dojo Construction | Wade | 4839 S Wander Lane, Holladay | Fireplace | 2 days |  | November | Dennis
23062 | Jorgensen Construction | Oliver | 6 Victoria Circle, Park City | Veneer | 2 months | 4000 | January | Chris
23063 | Dolphin Pools | Larson | 2141 Lindsey Lane, Holladay | hot tub veneer | 1 day |  | December | Dennis & Juan
5017

## 2022
Job # | Builder | Client's Name | Address | Description of work | Est. Duration | Ttl SF/LF | Approximate Start Date | Project Manager | Pre-Lien Req'd | Job status
22001 | Soul Garden | Roberts | 1427 Military Way | Stairs and paving | 1 month |  |  | Dennis
22002 | Magleby | Rankin | 22 Banner Court, Park City | fireplace | 2 days |  |  | Chris
22003 | Omega Pools | Privat | Promontory | pool coping | 2 days |  |  | Chris | no | closed
22004 | Magleby | Sorensen | 602 East Three Falls, Alpine | veneer | 9 months |  |  | Dennis
22005 | Hobble Creek | Duff Thompson | 447 South Carterville Road, Orem | veneer | 9 months
22006 | Diamond Philips | Mulholland | 1583 East New Bedford, SLC | landscaping | 1 month |  |  | Dennis
22007 | Craig Construction | Manire | 311 Colony, Park City | paving | 3 months | 5540 | May | Chris
22008 | Magleby | Clifford/Quail Hollow | 928 East Quail Hollow, Alpine | stone veneer | 4 months | 8979 | Mid July | Dennis
22009 | Magleby | Marlon | 7853 Hawk Ct, Park City | flagstone | 1 month | 1278 | mid april | Chris
22010 | Kent Construction | Reed | 5851 Shooting Star Circle, Heber | veneer | 2 months | 1168 | July | Chris
22011 | Kent Construction | Henderson | 4510 E Ridgeway CT, Kamas | veneer | 4 months | 6466 | August | Chris
22012 | Big D | Koslter | 7174 Lupine Dr, Glenwild Lot 96, Park City | veneer | 3 months | 5739 |  | Chris
22013 | Big D | DHD | 8945 Moonshadow, Empire Pass, PC | veneer | 3 months | 5771 |  | Chris
22014 | Kappus Landscape | Forkner | 10228 Altavilla Drive, Sandy | landscaping | 2 months | 5000 | July | Dennis
22015 | AMB | Zurcher | 2928 East Jennie Lane, Holladay | fireplace | 1 day |  |  |  | no
22016 | Jackson & Leroy | Mckinley | Wooded Cove, Holladay | veneer | 1 week | 100 |  | Dennis | no | closed
22017 | Big D | Welch | Glenwild 151, 530 Hollyhock st, Park City | veneer | 2 months | 5051 | July | Chris
22018 | Jackson & Leroy | Grigg | 2520 East Walker Lane, Holladay | veneer | 1 week | 350 | April | Chris | no | closed
22019 | Jackson & Leroy | Alan Meacham | 12857 Boulter Street, Draper | paving & FP | 2 weeks | 1200 | June | Dennis
22020 | Jackson & Leroy | Heather Miller | 2520 East Walker Lane, Holladay | veneer | 3-5 years | 50000 | June | Dennis
22021 | Tuck Landscaping/Schofield | Schofield | 2797 Craig Drive, SLC | paving | 2 weeks | 800 | May | Dennis | no | closed
22022 | Magleby | Appe | Glenwild | repair | 1 day |  | April | Chris | no | closed
22023 | Jackson & Leroy | Fuchs | 132 W Three Falls Ct, Alpine | veneer | 4 months |  | August | Dennis
22024 | Edgepoint Landscape | Lee | 262 North 350 West, Vineyard | paving | 2 weeks | 800 | May | Chris
22025 | Jackson & Leroy | Jeremy Jackson | 3900 S 2400 E, SLC | paving | 2 days |  | May | Dennis
22026 | Kappus Landscape | Dobson | 1589 East Tomahawk, SLC | paving | 3 weeks | 1100 | Fall | Dennis
22027 | Brandon Bodell | Hunt | 8 Dawn Hill, Pepperwood, Sandy | veneer |  | 12000 | June | Dennis | no
22028 | Magleby | Lambert | 11489 S Oberland, Sandy 8492 | veneer |  | 3600 | July | Dennis
22029 | Magleby | Ricks | 4393 Sheffield Dr. Provo | repairs | 1 day |  | May | Skip | no
22030 | Picot Landscaping | Nydeggar | 2870 Floribunda, Holladay | paving | 2 months |  |  | Dennis | no | closed
22031 | Kent Construction | Sloan | 6692 N Evening Star Crt, VR 256, Wasatch | veneer | 2 months | 4500 | July | Chris
22032 | Jackson & Leroy | Cutler | 8313 E Forest Creek rd, Heber | veneer | 8 montsh
22033 | Premier Restorations | James | 1347 Moyle Drive, Alpine | repairs | 2 weeks | 600 | July | Dennis & Juan | no
22034 | Clear Stone Builders | Miner | 276 N Clegg Canyon Dr, Mapleton | paving | 2 weeks | 700 | August | Dennis & Juan
22035 | JAL Pools | Petron | 5900 Brentwood Drive, SLC | pool coping | 2 days | 20 |  | Jose | no
22036 | RA Ferrin | Westwood | 14 West Westwood, PC | veneer | 2 weeks | 700 | July | Chris
22037 | Biltmore | Bateman | 2535 E Bracelona Dr, Sandy | fireplace | 2 days |  |  | Dennis
22038 | Kent Construction | Hoesleys | 2240 Lone Pine dr | repairs | 2 days |  | July | Chris | no | closed
22039 | Russel & Co | Huvall | 2508 Murray Holladay, Holladay | fireplace | 2 days | 90 | July | Dennis |  | closed
22040 | Craig Collins | Scott | 11979 S Nicklaus Dr, Sandy | veneer | 2 weeks |  | July | Dennis
22041 | Sunline Landscapes | Bywater | 4981 & 4979 Cottonwood Lane, Holladay | landscaping | 4 months |  | Fall | Dennis & Juan
22042 | Kappus Landscape | Lee | Lot 3 Two Creeks Lane, Park City | landscaping | 1 month | 1800 | october | Chris
22043 | Dolphin Pools | Rodman | Three Falls | Veneer pool | 1 week | 300 | August | Dennis
22044 | Steve Dubell | Mckay | 2324 Walker Lane, Holladay | firepit | 1 day |  |  | Dennis & Juan
22045 | Jackson & Leroy | Bowen | 2480 E Walker Lane, Holladay | repairs | 1 week |  | August
22046 | Jackson & Leroy | Murray | 6200 S Okd Orchard Lane, Holladay | Whitewash | 1week |  | August
22047 | Jackson & Leroy | Roberts | 1958 Claremont Way | fireplace | 1 day |  | August | dennis
22048 | Jackson & Leroy | Harwin | Park City | fireplace repairs | 2 days |  | july | Chris
22049 | Magleby | Colony 98 | White Pine, Colony 98, Park City | veneer repairs | 2 days |  | September | Chris
22050 | Establish Design | Establish Design | 3787 S Highland Dr, Millcreek | fireplace | 1 day |  | September | Dennis
22051 | Brandon Bodell | Larson | 2426 Maywood Cir, Salt Lake | veneer | 1 month | 700 | September | Dennis
22052 | Millhaven Homes | Robertson | 6324 West 9960 North, Highland | veneer | 3 months | 4000 | September | Dennis
22053 | Russel & Co | Evergreen Lot 1 | 7058 Silver Lake Drive, Park City | veneer | 6 months | 6500 | october | Chris
22054 | Spark Design | Darr | 1912 E Lakewood Dr, Holladay | fireplace | 1 day |  | october | dennis
22055 | Jackson & Leroy | Wright | 1076 South Bonneville Dr. SLC | firerock & brick | 1 month |  |  | dennis
22056 | Art Turner | Turner |  | fireplace | 1 day |  |  | dennis
22057 | Ezra Lee Design | Lot 57 | 2518 N Mountain Spring Ct. Alpine | Veneer | 2 years |  | 2023 | Dennis
22058 | Sunline Landscapes | Alan Meacham | 12857 Boulter Street, Draper | landscaping | 3 months |  | october | Dennis & Juan
22059 | Geoffrey Ruckel | Ruckel | 1440 E Laird Ave, SLC | fireplace | 3 days |  | october | dennis
22060 | J Studios | Chasson | 3360 Sun Ridge Dr, PC | fireplace | 2 days |  | November | Chris
22061 | Magleby | Earnest | 3047 Stewart Rd, Sundance | repairs | 3-5 days |  | october | Brent
22062 | Jackson & Leroy | Cowley | 482 N Waters Edge RD, Midway | veneer | 3 months |  | November | Chris
22063 | Brandon Black | Morgan | 2926 Stewart RD, Sundance | repairs | 2 days |  | october | Brent
22064 | Magleby | Vogel | Deer Crest | repairs | 1 month |  | November | Chris
22065 | Norman Const | Baus | 2741 East Ridgeway Dr, Lot 25. Tuhaye | veneer | 3 months |  | January | Chris
22066 | Norman Const | Guidotti | Lone Peak 34, Lone Peak Tuhaye | veneer | 3 months |  | January | Chris
22067 | Sunline Landscapes | Bearss | 1312 East 466 South, Alpine | landscaping | 2 days |  | September | Dennis
22068 | Jackson & Leroy | Mike Fields | Wolf Creek | repairs | 2 weeks |  | December | Chris & Juan
22069 | Kappus Landscape | Scruggs | 1448 Devonshire Drive, SLC | pool coping | 1 week |  | march | Dennis
22070 | Magleby | Harris Remodel | 1194 Moray Court | veneer | 2 months |  | March | Chris
22071 | Jackson & Leroy | Peterson Pool | 5042 Memory Lane, Holladay | pool coping | 1 month |  | March | Dennis
22072 | Jackson & Leroy | Caldwell | 6115 S Old Orchard Lane, Hollday | repairs | 3 days |  | December | Dennis & Juan
22073

## 2024
Job # | Builder | Client's Name | Address | Description of work | Est. Duration | Ttl SF/LF | Approximate Start Date | Project Manager | Pre-Lien Req'd | Job status
24001 | Chamberlain Homes | Babcock | 2426 & 2428 Walker Lane | Stone Veneer | 3 months | 4000 | January | Juan Leanos
24002 | Chamberlain Homes | Graham | Wolf Creek | Stone Veneer | 6 montsh |  | April | Chris
24003 | Chamberlain Homes | Marquardt | 1302 Canyon Oaks Way | Stone Veneer | 1 week | 120 |  | Dennis
24004 | Jackson Leroy | AMB | 4680 Kelly Circle | Stone Veneer | 1 week
24005 | Dave Meredith; Bright Living | Dave Meredith | 9 Apple Hill Circle, Sandy; Pepperwood | stone fireplace | 2 days |  | January | Dennis
24006 | Tekton | Vershcleiser | 9960 N Timpangos Crt, Tuhaye | Stone Veneer | 3 montsh | 5000 | February | Chris
24007 | Deven Johnson | Deven Johnson | 258 West 1290 South, Midway. Lot 6 Haven Farms | Stone Veneer | 6 months | 15000 | February | Chris
24008 | Cedar Valley Construction | Cox | 1736 South Preserve Dr, Mapleton | Stone Veneer | 6 months | 10000 | APril
24009 | JAL Pools | Red Maple | 4203 N Red Maple Cut, Lehi | Pool repairs | 2 weeks | 500 | March | Dennis/Jose
24010 | AMB Design |  |  | Bench | 1 day
24011 | Kappus Landscape | Hillary Taylor | 10181 Altavilla Dr, Sandy | Paving | 3 weeks | 1800 | May | Dennis/Jose
24012 | HCC | Gunther | 830 E 700 N, American Fork | Brick repairs | 1 week | 200 | February | Dennis
24013 | Jackson Leroy | Broadbent remodel | 2712 Hillsden Drive, Holladay | fireplace | 3 days |  | March | Dennis/Manolo
24014 | Jackson Leroy | Hopkins | 2459 Walker Lane | Block | 1 day |  |  | Dennis
24015 | Black Seal Builders | Peterson | 5882 Brentwood Dr. Holladay | fireplace | 2 days |  | April | Dennis
24016 | Vitruvius Design | Twin Peaks: CLose | 8955 N Twin Peaks Dr, Kamas | veneer | 1 month |  | Apil | Chris
24017 | Jackson Leroy | Bowen Golden Fleece | 2460 E Walker Lane | Hardscapes | 3 months |  | April | Dennis
24018 | Jackson Leroy | Hansen | 1137 Douglas St, SLC | Paving | 1 day |  | April | Dennis
24019 | Cedar Valley Construction | Gunther | American Fork | Veneer | 2 days |  | April | Dennis
24020 | Jackson Leroy | Danley | 4485 White Eagle Drive, Heber | repairs | 1 day |  | April | Chris
24021 | AMB Design | Fader | 8785 North Lookout Lane, PC | fireplace | 2 days |  | May | Chris
24022 | Aspen Lane Homes | Davies | 10850 Gambel Cove, Sandy | fireplace | 1 day |  | April | Dennis/Manolo
24023 | Russel & Co | Hoffman | 7647 East Moon Dance Circle, VR lot 292 | paving | 1 week |  | May | Chris
24024 | Kappus Landscape | Mullen | 1428 Ambassador Way, SLC | paving, hardscape | 2 weeks |  |  | Dennis/jose
24025 | Kappus Landscape | Schulte | 32 E Dartmoore Place, SLC | paving |  |  |  | Dennis/Jose
24026 | Arcsitio | Richard Gilbert | 4515 South Butternut, SLC | hardscape | 2 days |  | May | Dennis/Manolo
24027 | Chelsey Hale Design | Montgomery | 2041 E Copperbelt Dr, Heber City | fireplace | 1 day |  | may | Chris
24028 | Chamberlain Homes | Smith | 2285 Walker Lane, Holladay | Veneer, paving | 2 weeks |  | June | Dennis
24029 | Kappus Landscape | Gellert | 2310 E Walker Lane, Holladay | Fountain | 2 days |  | June | Dennis/Manolo
24030 | Heath Construction | Inn On The Hill | 225 S State Street, SLC | bench/paving | 2 days |  | May | Dennis/Manolo
24031 | Layton Construction | Dave Layton | Wasatch Peaks D22 | Stone Veneer | 3 months |  | July | Chris
24032 | Norman Construction | Brady | Lot 3N-5 Tuhaye | Stone | 2 months |  |  | Chris
24033 | Chamberlain Homes | Saunders Wright | 1978 Sheridan Rd, SLC | stone paving | 1 week |  | June | Dennis/Jose
24034 | Kent Construction | Barsh | 3130 American Saddler, Park City | Stone Veneer | 2 weeks |  | June | Chris
24035 | Kent Construction | Glier | 2184 E Lone Peak, Tuhaye | Stone Veneer | 4 months |  | January | Chris
24036 | Kevin Fitt | Hidden Park | 1685 E Creek Rd | Stone Veneer | 1 day |  | July | Dennis
24037 | Bickmore Construction | Clawson | 1130 Dutch Fields, Midway | Stone Veneer | 2 months |  | July | Chris
24038 | Sage Construction | Brunken | 1422 E Military Way, SLC | Stone Veneer | 2 months |  | July | Dennis/Jose
24039 | ASMS | Dennis Ralph | 1911 S 610 W Unit 1112 | home furnishing |  |  |  | Dennis
24040 | Jackson Leroy | Huntsman Remodel |  | fireplace | 2 days |  | July | Dennis/Manolo
24041 | Biltmore | Miles | 2384 E Delia Drive, SLC | fireplace | 2 days |  | July | Dennis/Manolo
24042 | RA Ferring | Vintage | Canyons PC | repairs | 3 days |  | July | Chris
24043 | Aspen Lane Homes | Towle | 1360 Elk Ridge Lane, Alpine | fireplace | 2 days |  | Augus | Dennis/Manolo
24044 | Build Utah/Russel | Monroe | 2695 Broken Spoke Way, PC | fireplace & ext repairs | 1 week |  | August | Chris
24045 | Kappus Landscape | Willette | 7002 Lupine Drive, Glenwild | door thresholds | 1 day |  | August | Chris
24046 | Kappus Landscape | Mancini | 1618 Millbrook Road, Millcrekk | stone paving | 1 week |  | September | Dennis/Jose
24047 | Robert Macarthur Design | Leishman | Bountiful | fireplace | 1 day |  | September | Dennis/Manolo
24048 | Jackson Leroy | Deer Crest 86 | Deer Crest 86, Wasatch County | Veneer, paving | 4 months |  | November | Chris
24049 | Jackson Leroy | Loci | 859 S 800 E, SLC, UT | Block veneer
24050 | HCC | Weidman | 4291 North Stone Crossing, Provo 84604 | fireplace | 1 day |  |  | dennis
24051 | Layton Construction | Layton | 2424 Walker Lane | Mailbox | 1 day |  |  | Dennis
24052 | Biltmore | Buchan | 5972 S Deerwood Creek Cir, Holladay | Veneer | 3 months |  | September | Dennis/Juan
24053 | Build Utah/Russel | Blaylock | 3006 E Thackeray Place, SLC | fireplace | 2 days |  | October | Dennis/Juan
24054 | Build Utah/Russel | Landau | 4450 S Matthews Way, SLC | fireplace & ext repairs | 3 days |  | October | Dennis/Juan
24055 | Omega Pools | Liljenquist | 4209 N Two Creeks Ln. Park City | pool copings | 3 weeks |  | August | Chris/Jose
24056 | Vitruvius Design | Lord | 9642 N Eagle View Crt, Wasatch County | veneer | 2 months |  | October | Chris
24057 | Elevated Homes | Valdez | 690 High Ridge Dr, Highland | Repair | 1 day |  |  | Dennis
24058 | Devereaux | Godfrey | 2282 E Shady Book Lane, SLC | fireplaces | 3 days |  | October | Dennis/Manolo
24059 | [7 empty] | Dennis/Juan
24060 | Magleby Remodel | Simmons or Colony 217 | White Pine 217, Park City | paving and coping | 3 weeks |  | October | Chris/Jose
24061 | United Contractors | Menlove | Midway | Brick veneer | 2 months |  | November | Chris/Martin Solid
24062 | HCC | Christensen | 2332 E Oakhill Circle, Holladay | Brick veneer | 2 months |  | November | Dennis/Martin
24063 | Biltmore | Macey | 2859 E Casto Lane, Holladay | 3 fireplaces | 1 week |  | November | Dennis/Manolo
24064 | JL | Walton | 2360 E Oakhill Dr, Holladay | stone paving | 1 day |  | November | Dennis/Martin
24065 | Jackson Leroy | Bergeson |  | fireplace & paving | 1 month |  | December | Chris
24066 | Killoween Construction | Welling | 422 N Waters Edge Rd, Midway | Stone Veneer | 2 montsh |  | April | Chris
24067 | Build Utah/Russel | Allarad | 6665 Broken Stick Court, Lot 146, Kamas | fireplace | 1 week |  | December | Chris
24068

## 2021
Job # | Builder | Client's Name | Address | Description of work | Est. Time
21000 | Jackson & Leroy | Ostler | 3677 South 2455 East, Millcreek | pool coping | 1 week
21001 | Jackson & Leroy | Seare | 6114 South Holladay Blvd, Holladay | paving and veneer | 2 months
21002 | Jackson & Leroy | Alger | 581 West 3700 North, Provo | veneer | 2 months
21003 | Jackson & Leroy | Snow | 1786 East Millbrook, Millcreek | pool coping | 1 week
21004 | Davies Design | Stanford | 130 Sunset Circle, Alpine | brick repairs | 2 weeks
21005 | Picot Landscaping | Nolan | 1710 East Devonshire, Salt Lake | pool coping | 1 week
21006 | AMB Design | Christensen | 2252 Melodie Ann Way, Holladay | fireplaces | 1 week
21007 | Annette Fazzino | Fazzino | 2181 E 5340 S, Holladay | mailbox | 2 days
21008 | Jackson & Leroy | Cavaletto | 14868 South Vintage View Lane, Draper | veneer | 1 week
21009 | Big D | Kings Crown | 1269 Rothwell Road, Park City | veneer | 1 week
21010 | Jackson & Leroy | Hansen | 1682 North 6250 East, Eden | pool coping | 4 days
21011 | Jackson & Leroy | Owen | 1828 Fort Canyon Road, Alpine | veneer | 9 months
21012 | Chamberlain Homes | Leiber | 2140 Parleys Terrace, Salt Lake City | patio | 1 week
21013 | Chamberlain Homes | Dunn | Colony, Park City | veneer | 5 months
21014 | AMB Design | Gardner
21015 | Jackson & Leroy | Barlow | 2380 East Cottonwood Lane, Holladay | veneer | 6 months
21016 | Cheryl Bullock Cleaning | Dunn | Provo | repairs | 1 day
21017 | Melissa Cutler | Cutler | 4975 Memory Lane, Holladay | pool coping | 1 week
21018 | Catherine Goodsell | Schmidt |  | fireplaces | 2 days
21019 | Magleby Construction | Milton | Woodland | pool coping | 3 day
21020 | Dolphin Pools | Christensen | Fayette | pool coping | 1 week
21021 | Jackson & Leroy | Jackson & leroy Office |  | wall | 1 week
21022 | Yamada Interiors | Yamada | Alpine | fireplaces | 3 day
21023 | Establish | Mcgarvey | 1739 E Millcreek Way, SLC | fireplace/patio | 1 week
21024 | Rob Mcarthur studios | Ricks | 4393 Sheffield dr. Provo | fireplace | 2 days
21025 | Tuck Landscaping | Liljenquist | 4209 N Two Creeks Ln. Park City | paving | 1 month
21026 | Sherman Bone | Hamula | 1801 Hubbard Ave, SLC | fireplace | 2 days
21027 | Biltmore | Chad Christensen |  | repairs | 2 weeks
21028 | Magleby Construction | Yuoh | Tuhaye | veneer | 6 weeks
21029 | Rob Mcarthur studios | Ricks | Victory Ranch | fireplaces | 2 weeks
21030 | Doug Knight | Cumbee | Deer Crest | fireplaces | 1 week
21031 | Brandon Bodell | Bradley | 672 Stokes Ave, Draper | veneer | 1 month
21032 | Jackson & Leroy | Miller | 1424 E Circle Way, SLC | fireplaces | 1 week
21033 | Dolphin Pools | Matthews | 15333 S Mountainside, Draper | pool coping | 1 week
21034 | AMB Design | Rodman | Three Falls Alpine | firepits | 2 days
21035 | Dave Larson | Cook Boathouse | South Fork | repairs | 2 days
21036 | Premier Restorations | James Marina | Alpine | fireplace | 1 day
21037 | Jackson & Leroy | Tim Fenton | walker lane | veneer | 1 month
21038 |  | Gustafson |  | repairs | 1 week
21039 | Smith Setjo | Christensen | Emigration canyon | fireplace | 2 days
21040 | Lindsay Spencer |  | Draper | fireplace | 2 days
21041 | Russel & Co | Utley |  | hearths | 1 day
21042 | Magleby Construction | Tittigier | 354 Centennial Circle, Park City | veneer | 1 month
21043 | Kappus | Drexel | 336 N Crestline Circle, SLC | patio | 1 week
21044 | Dolphin Pools | Church | 485 east 1500 N orem | pool coping | 3 day
21045 | Cottonwood Title | Frank Ivory | 2095 Maryland Circle, Holladay | patio | 1 week
21046 | Magleby Construction | Christensen | 150 E 200 S, Fayette | veneer | 2 months
21047 | Jackson & Leroy | Helm Home | Park City | repairs | 1 day
21048 | AMB Design | Flanagan | SLC Condo | fireplaces | 2 weeks
21049 | AMB Design | George | Lot 27 White Pine Colony, PC | fireplaces | 1 month
21050 | Norman Const | Canzano | Tuhaye | veneer | 1 month
21051 | Picot Landscaping | Dreyfus |  | landscape | 2 weeks
21052 | Jackson & Leroy | Browning | 1136 E Gilmer drive, SLC | repairs | 3 days
21053 | Cliff Goldthorpe |  | Tuhaye lot 3N-6 | veneer | 2 months
21054 | Jackson & Leroy | Crosland | Holladay | fireplaces | 1 week
21055 | Timberridge Custom | Trimble | Red Ledges | fireplaces | 1 week
21056 | Stoneybrook Homes | Stoneybrook | 872 East 13450 South, Draper | fireplace | 3 days
21057 | Biltmore | Theurer | 1128 Bonneville Dr, SLC | fireplaces | 2 days
21058 | Sunline | Heglar | 2384 E Field Rose Dr, Holladay | landscape | 2 months
21059 | Craig Construction | Killion | Colony 246, Park city | paving | 2 months
21060 | Detailed Landscape | Ward | 6513 Weber Canyon, Oakley | veneer | 2 weeks
21061 | Lecate Designs | Turner | Salt Lake | fireplace | 2 days
21062 | Lecate Designs | Critchfield | Salt Lake | Fireplaces | 4 days
21063 | Lecate Designs | Buckner | Salt Lake | fireplaces | 2 days
21064 | RA Ferrin | Pinebrook | Pinebrook, Park City | block | 1 day
21065 | Jackson & Leroy | Parker | Park City | veneer | 2 weeks
21066 | Jackson & Leroy | Don Pugh | 2304 S Oneida St, SLC | repairs | 2 days
21067 | Doug Knight | Taylor | Promontory | fireplace | 2 days
21068 | Andrew Menlove | Steve State | SLC | fireplace | 2 days
21069 | Anderson Consulting | Todd Peterson | Orem | repairs | 1 day
21070 | Dolphin Pools | Hales |  | pool coping | 1 week
21071 | Picot Landscaping | Miller |  | paving | 1 week
21072 | Kent Construction | Reed | Victory Ranch | veneer | 2 months
21073 | Kent Construction | Henderson | Tuhaye | veneer | 3 months
21074 | Jackson & Leroy | Davis | Military Way | veneer | 1 week
21075 | Phelps Construction | Hawkes | Red Ledges | fireplaces | 1 week
21076 | Magleby Construction | Asay | vivian park | repairs | 1 day
21077 | Magleby Construction | Colony 253 | 253 Colony | block | 2 days
21078 | Chamberlain Homes | Colon 72 Cohen | Colony Lot 72, Park City | floors | 3 weeks
21079 | Hobble Creek | Demordaunt | Alpine | fireplace | 2 days
21080 | Norman Const | Zigman | Tuhaye | veneer | 3 months
21081 | Norman Const | Pearson | Colony lot 15, park city | veneer | 3 months
21082 | Jackson & Leroy | Tate | 2015 Regal Stream CV, Salt Lake | repairs | 2 weeks
21083 | Tuck Landscaping | Bishop | 6190 South Murdoch Woods Place, SLC | landscape | 1 week
21084 | Biltmore | Kehl | 5888 South Deerwood Crk, Holladaay | veneer | 3 months
21085 | Russel & Co | Graham | Salt Lake | caps | 3 days
21086 | Establish | Skonnard | Alpine | table | 1 day

## 2020
Job # | Builder | Client's Name | Address | Description of work | Est. Time
20001 | Magleby Construction | Beck | Quarry Mountain Road, PC | veneer | 4 months
20002 | Magleby Construction | Stonegate 55 | Stonegate 55, Provo | veneer | 2 months
20003 | Magleby Construction | Gardner Garage | Wolf Creek 67 | veneer | 3 weeks
20004 | Jackson & Leroy | Pingree | Holladay blvd | repairs | 1 day
20005 | Jackson & Leroy |  | 1904 E Mystic Cove | repairs | 1 day
20006 | Jackson & Leroy | Kimball | 105 Pfeiferhorn | repairs | 1 day
20007 | Jackson & Leroy | Leroy | 11291 Emerson Circle, Alpine | patio | 1 month
20008 | Hacking Construction | Knight Bldg | 381 E Center Street | repairs | 1 month
20009 | Jackson & Leroy | Peterson | 5042 S Memory Lane | patio & fireplace | 1 month
20010 | Jackson & Leroy | Dildy | 2766 Bitterbrush Dr, Promontory | veneer | 2 months
20011 | Magleby Construction | Wheat | White Pine | repairs | 1 day
20012 | AMB Design | Barton | 4670 Kelly Circle, Holladay | trims | 1 week
20013 | Magleby Construction | Cook | 1101 W 2600 N, Pleasant Grove | veneer | 8 months
20014 | Jackson & Leroy | Caldwell | 6115 Old Orchard lane, holladay | veneer | 4 months
20015 | Jackson & Leroy | Hillary taylor | Altavilla, Sandy | patio repairs | 1 month
20016 | Jackson & Leroy | Bullen | Cottonwood Lane, Holladay | veneer | 4 months
20017 | Hobble Creek Const | Dominguez | 3 Falls, Alpine | veneer | 2 months
20018 | Jackson & Leroy | Doran Taylor | SLC | repairs | 1 week
20019 | Premier Restorations | Olson | Stonegate, Provo | landsacpe | 1 week
20020 | Jackson & Leroy | Skonnard | 2304 North Three Falls Dr, Alpine | veneer | 12 months
20021 | Jackson & Leroy | Helm | Quarry Mountain Road, PC | veneer | 12 months
20022 | Jackson & Leroy | Harrison | 7988 English Oaks, Sandy | repairs | 2 day
20023 | Mansfield | Mansfield |  | patio | 3 weeks
20024 | RA Ferrin | Zigg | Frostwood | landsacpe | 1 week
20025 | Michael Daniels | Michael Daniels | 3397 South Oakwood, Millcreek | patio | 2 weeks
20026 | Jackson & Leroy | Griggs | Deer Valley | veneer | 2 weeks
20027 | Jackson & Leroy | Kevin Pearson | 1485 Penrose Drive, SLC | landsacpe | 2 weeks
20028 | Jackson & Leroy | Resta | 3925 Mount Olympus Way, Millcreek | cmu, veneer | 4 months
20029 | Spencer Eccles | Eccles | Park View, Olympus | repairs | 3 days
20030 | Biltmore | Gregg Christensen | Kentucky Ave, Holladay | landsacpe | 3 months
20031 | Tuck Landscaping | Tim Fenton | 5508 Walker Lane, Holladay | repairs | 1 week
20032 | Magleby Construction | Oh | Wolf Creek | repairs | 2 day
20033 | RA Ferrin | Hopkins | Preserves | veneer | 2 weeks
20034 | Andrew Menlove | Harrison | Holladay | firebrick | 3 days
20035 | Dolphin Pools | Jeff Ludlow | 6091 S Seville Vista Cove, Murray | pool coping | 1 week
20036 | Russ Taylor | Mika | Wolf creek 68 | repairs | 1 week
20037 | Zwick Construction | Darin Zwick | 2260 Parleys Terrace, SLC | patio, pool | 6 week
20038 | AMB Design | Lowe | 2416 E 900 S, SLC | fireplaces | 1 week
20039 | Hobble Creek Const | Lee | 968 East Quail Ridge, Alpine | brick | 8 weeks
20040 | AMB Design | Miller Cottage | walker lane, Holladay | fireplace, paving | 1 week
20041 | Jackson & Leroy | Mirsky | 1770 N Trappers Loop, Heber City | veneer | 6 months
20042 | Magleby Construction | Lisonbee Ranch | 1536 North Wolf Creek Ranch Rd, Woodland | veneer | 3 months
20043 | JLR Contractors | Blake Roney | 3187 N Foothill Dr. Provo | repairs | 2 weeks
20044 | Norman Const |  | Tuhaye | repairs | 2 weeks
20045 | Russel & Co | Kindel | 9422 S Granite Trail Lane, Sandy | veneer | 2 months
20046 | Magleby Construction | Dunn | Provo | repairs | 1 day
20047 | Jackson & Leroy | James Huntsman | 1452 Military Way | repairs | 2 days
20048 | Hacking Construction | Halladay | 2976 Meadows Drive, Sundance | patio | 1 day
20049 | Jackson & Leroy | Simmons | Sundance | repairs | 2 days
20050 | Jackson & Leroy | Pugh | 2304 S Oneida, SLC | repairs | 1 day
20051 | Kappus | Dunn | 1809 Mystic Meadow Cove, Cottonwood Height | patio, pool | 1 month
20052 | Dolphin Pools | Cook Pool | 1101 W 2600 N, Pleasant Grove | pool coping | 1 week
20053 | AMB Design | Cris Aston | Sandy | fireplace | 2 days

## 2019
Job # | Builder | Client's Name | Address | Description of work | Est. Time
19001 | Jackson & Leroy | Mecham | Connecticut Avenue, SL | architectural stone | 3 months
19002 | Jake Jorgensen | BMK | Red Ledges | veneer | 2 months
19003 | Andrewe Menlove | Menlove | Holladay | firebrick | 3 days
19004 | Magleby Remodel | Reynolds | 330 Matterhorn Drive, PC | fireplace | 3 days
19005 | Hobble Creek | Fuller |  | fireplace | 2 days
19006 | Fox Group | Brasher | 4990 South Fairbrook | fireplace | 1 day
19007 | Kuemel Designs | Carlson | Lot 31 Preserves | veneer | 4 months
19008 | Steve Dubell | Toscano | 3146 Canyon Oak, Sandy | fireplace | 2 days
19009 | Chamberlain | Gobert | Carrigan Canyon | Block | 3 days
19010 | Chamberlain | Ward | Oakley | veneer | 2 months
19011 | Dolphin Pools | Gobert | Carrigan Canyon | pool copings | 2 weeks
19012 | Jackson & Leroy | Wardle | 3817 Lares Way | repairs | 1 day
19013 | Magleby Remodel | Rawles | Orem | repairs | 2 days
19014 | Magleby Remodel | Volstad | Glenwild | repairs | 2 days
19015 | Magleby Remodel | Sommer | Pepperwood | repairs | 2 days
19016 | Slager | Slager | 1427 Penrose | paving | 3 weeks
19017 | Jackson & Leroy | JMK Huntsman | 1605 New Bedford, SLC | paving | 1 week
19018 | Jackson & Leroy | Thomas | 4304 S Wander Lane, Holladay | veneer | 3 months
19019 | Fox Group | Keith Taylor | Walker Lane | paving | 2 months
19020 | Jackson & Leroy | Carol Smith | 2459 E Field Rose Dr, SLC | veneer & paving | 1 month
19021 | Magleby Construction | Cook Boathouse | South Fork Canyon | veneer | 2 months
19022 | Jake Jorgensen | Appel | Hideout | veneer | 1 month
19023 | Jeff Shaw | Watts |  | fireplcae | 2 days
19024 | Jackson & Leroy | Lund | 3899 N Riverwood, Provo | landscape | 3 months
19025 | Stonybrook homes |  | Victory Ranch | fireplace | 2 weeks
19026 | Hobble Creek | Gardner | 3 falls, Alpine | veneer | 2 months
19027 | Russel & Co | Allred | 6112 Old Orchard Lane, Holladay | veneer | 2 months
19028 | Spencer Eclles | Eccles | 4075 Oakview | repairs | 2 days
19029 | Magleby | Hemmersmier | North cove | veneer | 3 months
19030 | AMB | Miles | Holladay | fireplace | 3 days
19031 | AMB | Rick white | olympus cove | fireplace | 2 days
19032 | Edge Builders | Kimmelman | Powder Mountain | patio | 1 month
19033 | Edge Builders | Miller | Promontory | repairs | 2 months
19034 | RA Ferrin | Sherry | Glenwild | repairs | 1 day
19035 | Fox Group | Godfrey | 2439 Olympus Drive, SLC | veneer, patio | 3 months
19036 | Jackson & Leroy | Spencer | 8006 Sunrise Loop, Park City | veneer | 3 months
19037 | Walt Orlowski |  | Deer valley | repairs | 2 days
19038 | Jackson & Leroy | Rick white | olympus cove | repairs | 1 week
19039 | Smart | Gardner | Fish Haven, Idaho | veneer | 1 month
19040 | Hobble Creek | Wong | 5937 W Chatham Cir, Highland | repairs | 1 day
19041 | AMB | Karen Romney |  | fireplace | 1 day
19042 | Catherine Goodsell | Harper |  | fireplace | 2 days
19043 | Kappus Landscape | Swindel | Harvard ave | patio | 1 month
19044 | AMB | Miller | Pepperwood | fireplace | 2 days
19045 | Jackson & Leroy | Parkin | Timberlakes, heber | veneer | 6 months
19046 | Magleby | Blunck |  | veneer | 6 months
19047 | AMB | Briggs | Vashon island | fireplace | 2 days
19048 | Dolphin Pools | Lynwood pool | Lynwood, provo | pool copings | 2 weeks
19049 | Catherine Goodsell | Bobby smith | shadow wood lane | fireplace | 2 days
19050 | Lowell | McSlarrow | 3162 East Eagle View Circle, Sandy | patio | 2 weeks
19051 | Picot | Keller |  | patio | 2 weeks
19052 | Jackson & Leroy | Gaylord | 2321 E 1300 S, SLC | patio | 2 weeks
19053 | RA Ferrin | Ferrin | 14 Westwood, Park city | veneer | 2 months
19054 | Norman Const | Landis | 33 Colony | repairs | 2 days
19055 | Kim Topham | Kim Topham | Alpine | fireplace | 2 days
19056 | Jackson & Leroy | Bowman | 7173 E Moonlight Dr, Kamas | veneer | 3 months
19057 | Dolphin Pools | Michael Jordan | 36 Glenwild | repairs | 1 week
19058 | Magleby | Davis | Wolf Creek | firebrick | 2 days

## 2018
Job # | Builder | Client's Name | Address | Description of work | Est. Time
18001 | AMB Design | Relyea | Pepperwood | fireplace | 1 day
18002 | Jackson & Leroy | Jeremy Jackson | Arnette | patios | 3 weeks
18003 | Jackson & Leroy | Hawks | 5457 Cottonwood Clud Dr, Holladay | repairs | 1 day
18004 | Hobble Creek Const | Ferguson | Oakley | veneer | 1 month
18005 | Magleby Remodel | Wilson | 1017 waterford, Provo | fireplaces | 2 week
18006 | Jackson & Leroy | Fenton | 5342 S Wooded Cove, Holladay | veneer | 6 months
18007 | Jackson & Leroy | Bearss | 1312 E 466 S Alpine | patios | 2 months
18008 | Jackson & Leroy | Broadbent | 2712 Hillsden Drive | landscaping | 6 months
18009 | magleby Construction | Highlands Ranch | Wolf Creek 22 | veneer | 3 montsh
18010 | Park City Mtn Builders | Broken Spoke | 2710 Broken Spoke Way, PC | block, veneer | 1 month
18011 | AMB Design | Scharmann | Pepperwood | fireplaces | 2 week
18012 | Fox Group | Andrus | Holladay | fireplace | 1 day
18013 | Jen Mangum Design | Hunter | Heber | fireplace | 1 week
18014 | magleby Construction | Chad Magleby | 427 East 70 North, Lindon | veneer | 1 month
18015 | magleby Construction | Gardner | Wolf creek 67 | veneer | 1 week
18016 | magleby Construction | Urban | Peoa | veneer | 2 months
18017 | Dolphin Pools | Brown | Holladay | pool coping | 1 week
18018 | magleby Construction | Devore | South Fork Canyon | repairs | 1 week
18019 | Park City Mtn Builders | SH15 | Soaring hawk 15, hideout | veneer | 2 week
18020 | Dolphin Pools | Henry | 13378 Aintree Hill, Draper | veneer | 1 week
18021 | Gardner Group | Sederman | Colony 210 | veneer | 2 months
18022 | LUX Builders | Deboes | 181 East 4th Ave, SLC | thin brick | 2 days
18023 | Park City Mtn Builders | Soaring Hawk 23 | Soaring hawk 23, Hideout | veneer | 2 week
18024 | Park City Mtn Builders | Hideout 36 | 904 E Longview Dr, Lot 36, Hideout | thin veneer | 2 week
18025 | Magleby | Beck |  | repairs | 1 day
18026 | Magleby | Whisenant | 1023 Sunbrook Circle, Alpine | repairs | 1 week
18027 | Russ Taylor | Ron Mika | Sunbrook Circle, alpine | repairs | 1 week
18028 | AMB Design | Allred | Manhattan beach | fireplace | 2 days
18029 | Jackson & Leroy | Elliott Taylor | Walker Lane | paving | 1 month
18030 | Jackson & Leroy | Jon Schwartz | 2855 E Canyon View Dr. Millcreek | paving | 3 days
18031 | Ivory Custom Homes | Clark Ivory | Walker Lane | veneer | 1 month
18032 | Jackson & Leroy | Smith | Field rose | repairs | 1 day
18033 | Jackson & Leroy | Simmons | Sundance | repairs | 2 days
18034 | PCMB | Hideout 16 | Glistening ridge 16 | veneer | 2 week
18035 | Jackson & Leroy | Robertson | 9810 Martha Rd, Alta | repairs | 1 week
18036 | Fox Group | Deaton | 1869 Siesta Drive, | fireplace | 2 days
18037 | Hacking Construction | Birritella | Deer Run Drive, Sundance | patio, landscape | 2 months
18038 | Magleby | Summit Vista | 3360 West 6200 S, Taylorsville | BBQ cmu | 2 days
18039 | Jackson & Leroy | Weichar | 1270 Country manor, alpine | fireplace/pavers | 1 month
18040 | Big D | Conway | 2505 White Pine Lane, PC | veneer | 3 montsh
18041 | Jackson & Leroy | Bowen | Walker Lane | repairs | 3 days
18042 | Biltmore | Clayton |  | paving | 3 days
18043 | Jackson & Leroy | Hopkins | Haven Lane | Firerocks | 2 week
18044 | Picot | Schenk | Military way | paving | 1 month

## 2017
Job # | Builder | Client's Name | Address | Description of work | Est. Time
17001 | Craig Construction | Bronfman | Red Fox, Preserves | veneer | 3-4 months
17002 | Biltmore | Smylie | Haven wood lane | firerocks | 1 week
17003 | AMB Design | Schuler | Wolf Creek | table | 1 day
17004 | Magleby | Smith | 276 East 4000 North, Provo | brick | 1 week
17005 | Hobble Creek | Higgs | 171 East 3rd Avenue, Unit 602 | brick repair | 2 days
17006 | Chamberlain Homes | Mark Miller | Carrigan Canyon | repairs | 1 day
17007 | Tolton | Tolton | 640 Eaglepoint Drive, NSL | fireplace | 2 weeks
17008 | Sheldon Killpack | Killpack | 2475 E 475 N. Layton | surrounds | 1 month
17009 | Dolphin Pools | Watts | 2250 East 5340 South, holladay | Bluestone coping | 1 week
17010 | Ivory Homes | Clark Ivory |  | bluestone coping/paving | 6-8 weeks
17011 | Magleby | Harris | 2202 East HWY SR 35, Woodland | veneer | 6 months
17012 | Jackson & Leroy | Hardy | Quarry Mtn Rd, Park City | veneer | 2 montsh
17013 | Jackson & Leroy | Advocates Law | holladay | architectural | 3 weeks
17014 | Jackson & Leroy | Shadle | Hideout canyon | veneer | 3 months
17015 | Biltmore | Chad Christensen | holladay | patio | 3 day
17016 | Dolphin Pools | Heyland |  | coping | 1 week
17017 | Jaffa Group | Jacobs | american saddler | fireplace | 2 days
17018 | Chamberlain Homes | Marquardt | North cove | repairs | 2 days
17019 | AMB Design | Radant | red fox, glenwild | architectural | 3 day
17020 | ELK Design | Cathy Young | sandy | fireplace | 1 day
17021 | Premier Restorations | Glenn | 500 South, midway | repairs | 1 day
17022 | AMB Design | Macey | 10230 N summit View dr. PC | fireplaces | 2 weeks
17023 | Jackson & Leroy | Freedman | Military way, SLC | veneer | 1 week
17024 | Jackson & Leroy |  | 2180 E Wooded cove | repairs | 1 day
17025 | Magleby | Baliff | Birch st, provo | architectural | 2 days
17026 | Jackson & Leroy | Broberg | Provo | repairs | 1 week
17027 | RA Ferrin | Hopkins | Preserves, Park City | veneer | 2 months
17028 | Jackson & Leroy | Eccles | Millcreek lane | patio | 1 month
17029 | Jackson & Leroy | Kimball | 105 South Pfeifferhorn, Alpine | patio | 2 weeks
17030 | Spencer Eccles | Spencer Eccles | 4075 Oakview Drive, SLC | repairs | 2 days
17031 | Magleby |  | 4768 N Verona Crt | repairs | 3 day
17032 | Premier Restorations | Josh James | Moyle Drive, Alpine | veneer | 6 weeks
17033 | Jackson & Leroy | Baugh | Berkshires | plinth installation | 1 day
17034 | Seven Star Ranch | Mika | alpine | bbq | 2 days
17035 | Jackson & Leroy | Brooks Hansen | Wanship | repairs | 1 day
17036 | Magleby | Greenwald | promontory | warranty | 2 days
17037 | Kirkham MGMT | Rasband | Wolf Creek | repairs | 2 days
17038 | Kirkham MGMT | Checketts | Wolf Creek 12 | repairs | 3 days
17039 | Chamberlain Homes |  |  | repar | 1 day
17040 | RA Ferrin | Frostwood |  | veneer | 3-4 months
17041 | Mindy Gertler | Josh James | Moyle Drive, Alpine | repairs | 3 days
17042 | Jackson & Leroy | Hansen | Eden | repairs | 2 days
17043 | Magleby | Gardner lights | Wolf creek 67 | pillars | 3 days
17044 | Jackson & Leroy | Mansfield | 1428 circle way, SLC | patio | 1 week
17045 | Jackson & Leroy | Sorenson | holladay | patio | 6 weeks
17046 | Smart Construction | Jensen | Laketown, Bear Lake | patio | 1 month
17047 | Norman Const | Landis | lot 33 colony | repairs | 1 day
17048 | GS Excel | Freed | Weber canyon | veneer | 3 months
17049 | Picot | Eccles | 1720 E Yalecrest | repairs | 1 day
17050 | Magleby | Bilger | 2978 Saddleback Ridge, Promontory | repairs | 1 week
17051 | Jackson & Leroy | Evans | Bald Eagle drive, PC | fireplace | 1 week
17052 | russel & Co | Osher | victory ranch | veneer | 3 months
17053 | russel & Co | Grubbs | victory ranch | veneer | 3 months
17054 | AMB Design | Jones | 2045 E Sycamore Lane, Holladay | fireplace | 1 day
17055 | AMB Design | Bright Living |  | fireplace | 2 days
17056 | AMB Design | Gardiner | Bakersfield CA | fireplace | 0
17057 | Shannon Wright | Little | 241 Colony | fireplaces | 0
17058 | Magleby | Stein | Stein remodel, Deer valley | fireplaces | 1 week
17059 | Jackson & Leroy | Heinz |  | firerock | 3 days
17060 | Chamberlain Homes | Wheelwright | Oakley | fireplace | 2 weeks
17061 | Edge Builders | Jonas | Park City | veneer | 2 months
17062 | Edge Builders | Lot 39 | Lot 39 Powder Mountain, Eden | veneer | 2 months
17063 | russel & Co |  | 1027 S Vista View | brick repair | 2 days
17064 | Jackson & Leroy | Rosenberg | 2540 Haven Lane, Holladay | veneer | 6 months
17065 | Park City Mt Builders | lot 22 | Hideout canyon lot 22 | veneer | 1 month
17066 | Adams Construction | Chipman | 1682 W 900 N, Provo | veneer | 6 months
17067 | Establish Design | Rasmussen | 1636 Orchard Drive, SLC | patios | 2 months
17068 | Jackson & Leroy | Young | 2360 East Oakhill Drive, SL | veneer | 3 months
17069 | Magleby | Gentry | 2408 Stuart Drive, Sundance | fireplace | 2 days
17070 | Magleby | Robertson |  | fireplace | 1 week
17071 | Jackson & Leroy | Wales | 2011 Pheasant way | repairs | 1 day
17072 | Jackson & Leroy | Fenton repairs | 5508 Walker Lane estates | repairs | 2 days
17073 | Magleby | Lynwood | Lynwodd Drive, Provo | veneer, patios | 6 months
17074
17075
17094 | Big D | Olch | Colony 94 | CMU/stone veneer | 6 months
17152 | Big D | VR 152 | victory ranch lot 152 | stone veneer | 3 weeks
17153 | Big D | VR 153 | victory ranch lot 153 | stone veneer | 3 weeks

## 2016
Job # | Builder | Client's Name | Address | Description of work | Est. Time
16001 | J&L |  | 8768 S grand oak, sandy | repairs | 1 day
16002 | J&L | Barton |  | fireplace | 2 days
16003 | Mjay | Mjay |  | veneer | 1 days
16004 | Wathen |  |  | trim | 2 days
16005 | MR Brugge | Goldberg-Giodotti | 5360 cove hollow, park city | veneer | 2 months
16006 | Magleby | jimmy | 84 S country manor | repairs | 1 day
16007 | Cameo | Ord | Lot 7 Wolf Creek | veneer & pavers | 8-9 months
16008 | Biltmore | Ben Romney | 2402 E Pheasant Way | walls | 3 months
16009 | Magleby | Call-Corcoran | Lot 38 Colony | veneer | 6 months
16010 | Biltmore | Schaeffer |  | firerock | 1 week
16011 | Cameo | Corr | Lot 38 Wolf Creek, 2322 N westward Ho | CMU | 2 weeks
16012 | Big D | Glenwild entry | Glenwild entry | stone | 1 week
16013 | Big D | Victory Ranch 132 | Victory Ranch 132 | veneer | 1 month
16014 | Cameo | Quinton | 906 Coldwater way, Midway | fireplaces | 1 week
16015 | Jaffa Group | Wright | 35 Sandstone crt, PC | fireplace | 2 days
16016 | RA Ferrin | Luke |  | repairs | 1 day
16017 | Chamberlain | Durham | holladay blvd | repairs | 1 week
16018 | Chamberlain | Jane Marquardt | 42 Knightsbridge lane | repairs | 1 week
16019 | Chamberlain | Brawner | Deer Valley | veneer | 2 months
16020 | Chamberlain | Christensen |  | repairs | 1 day
16021 | Signature Pools | Art wing | 482 riverwood circle | repairs | 1 day
16022 | Jaffa Group | Richard Jaffa | 2405 Meadows drive | fireplace | 1 day
16023 | Miller Const | Harmony Health | Park city | veneer | 3 months
16024 | Magleby | Scott Brown | Provo | fireplace | 1 week
16025 | Magleby | Rosenvall | Riverton | fireplaces | 2 weeks
16026 | Magleby | Palmierri | vintage, provo | veneer | 5-6 months
16027 | Hobble Creek | Henderson | sugarhouse | brick repairs | 2 days
16028 | Dave Spafford | Dave Spafford | 2750 East Creek Crossing | repairs | 4 days
16029 | Signature Pools | Kade Huntmsan | Holladay | veneer | 2 days
16030 | AMB Design | Walker | Holladay | fireplace | 2 days
16031 | Silver Strike Lodge | Silver strike | Deer Valley | repairs | 2 days
16032 | J&L | King | Carrigan Canyon | veneer | 1 month
16033 | J&L | Carter | Emigration canyon | patio & veneer | 2 months
16034 | J&L | Hollands |  | patio trim | 1 day
16035 | Magleby | Dittmer | 5129 N Silver Springs Rd, PC | CMU | 1 day
16036 | Spencer Eccles | Spencer Eccles | Park View drive, Salt Lake | repairs | 1 week
16037 | CSM | Timbrook | Colony 176 | repairs | 1 day
16038 | RS Hardman | Mendelson | 60 Promontory | veneer | 2 weeks
16039 | Mark Miller | Miller | Carrigan Canyon | repairs | 2 days
16040 | Picot Company West | Marsden | Salt lake | patios | 1 week
16041 | Steve Dubell | Horvath | 10287 Deer crest | sign | 1 day
16042 | Andersen Consulting | Pedersen | 400 North Orem | repairs | 1 week
16043 | AMB Design | Nantz | Peeble Beach CA | hood | 1 week
16044 | Magleby | Oh | Wolf creek | repairs | 1 day
16045 | Magleby | Harris | River Road, Woodland | veneer | 6 weeks
16046 | Picot Company West | Price | 3664 Solamere Drive, PC | patios | 6 weeks
16047 | Lowell Const | Mcslarrow | 3162 Eagle View Cir, Sandy | patio | 2 weeks
16048 | Noorda | whitby | 924 East 200 South, SLC | brick repairs | 2 days
16049 | Chamberlain |  | 34 Sandstone court, PC | repairs | 3 day
16050 | Big D | Victory Ranch 150 | VR 150, 6607 E Broken Stick crt, kamas | veneer | 3 weeks
16051 | Big D | Victory Ranch 151 | VR 151, 6599 E Broken Stick crt, kamas | veneer | 3 weeks
16052 | Big D | Victory Ranch 130 | VR 130, 6776 E Riparian way | veneer | 3 weeks
16053 | Big D | Victory Ranch 139 | VR 139, 6739 E.Riparian way | veneer | 4 weeks
16054 | Big D | Victory Ranch 140 | VR 140, 6741 E Riparian way | veneer | 5 weeks
16055 | Big D | Victory Ranch 155 | VR 155, 6555 E Broken Stick crt, kamas | veneer | 3 weeks
16056 | RA Ferrin |  | 2335 Lakeline Drive | patio | 2 weeks
16057 | Magleby | Paras |  | CMU | 1 day
16058 | Magleby | Beck | Pepperword | veneer | 3 weeks
16059 | Magleby | Flowers | 185 Colony | fireplace | 1 week
16060 | J&L | Fowles | 4145 N 900 W, Pleasant grove | floors, caps, misc | 2 months
16061 | J&L |  | 2857 E Willow crt | repairs | 1 day
16062 | Chamberlain | Priskos | Cottonwood lane | repairs | 1 week
16063 | J&L | Jon Huntsman | New Bedford | firebrick | 1 day
16064 | Chamberlain |  | 7909 woodland drive, park city | repairs | 1 day
16065 | Dolphin Pools | Eckstrom Pool | 2832 north 550 West, Pleasant Grove | pool/spa coping | 2 weeks
16066 | Hacking Construction | Eckstrom Landscaping | 2832 north 550 West, Pleasant Grove | landscaping/patios | 6 weeks
16067 | Magleby | Woods | Alpine | repairs | 2 days
16068 | Larry Cohen | Larry Cohen | Colony 49 | repairs | 2 days
16069
16197 | W Lowery | Smithson | 197 Colony | veneer | 4-5 months

## 2015
Job # | Builder | Client's Name | Address | Description of work | Est. Time
15001 | Keller | Gay | Parley's Terrace Way | Fireplace surrounds | 3 days
15002 | Big D | D'urso | Snyderville | Veneer | 2 months
15003 | Magleby Remodel | Cuillard | 6768 W 10125 N, Highland | Fireplace veneer | 3 days
15004 | Dubell | Zenger | 1593 Federal Point | fireplaces | 2 days
15005 | Premier Restorations | Beebe | Midway | repairs | 1 day
15006 | AMB | Sandee Smith | 987 E Old English Rd. Draper | fireplaces | 5 days
15007 | Russell and Co. | Richerson | Lot 55 Mayfly, Victory Ranch | Veneer | 1 month
15008 | Russell and Co. | Lot 31A | Lot 31A, Victory Ranch | Veneer | 1 month
15009 | Morgan | Nathen Morgan | 1529 Yale Ave, SLC | patios | 1 month
15010 | J&L | Mckinley | Cottonwood Lane | Veneer | 1 month
15011 | Waters Edge |  | Park city | Veneer | 2 days
15012 | Dolphin Pools | Holmes | 4818 S Viewmont, Holladay | pool coping | 3 days
15013 | Magleby | Gardner Caretaker | Wolf Creek 67 | Veneer | 6 weeks
15014 | Gardner Group | Spec home | Lot 242, Colony | Veneer | 4 months
15015 | Ron Dallin | Ron Dallin | Sundance | fireplace | 1 week
15016 | Dolphin Pools | Austin | 284 Twin river loop, alpine | pool coping | 1 week
15017 | Magleby Remodel | Bailey | Highland | repairs | 3 hours
15018 | Doug Knight | O'brien | Deercrest | pool coping and patio | 2 months
15019 | Magleby Remodel | Saddler | 5963 West Horizon, Highland | repairs | 2 days
15020 | Steve Dubell | Willey | 2550 Maywood, SLC | fireplace | 1 day
15021 | Gardner Group |  | 3333 meadows drive | 14.5 | 1 day
15022 | J&L | Cohen | Cottonwood Club lane | Veneer | 1 month
15023 | J&L | Baugh | Berkshires | repairs | 3 days
15024 | Jennifer Truong Design | Lehr |  | fireplace | 2 days
15025 | Amy Reid | Amy Reid | 1477 Harvard Ave | patios | 3 days
15026 | K Rocke Interiors | Kristen Rocke | Holladay | fireplace | 1 day
15027 | Alice Lane Designs | Judy Olsen | 3620 Hillside lane, holladay | patios & fireplace | 2 weeks
15028 | GS Excel | Dawson |  | fireplace | 3 days
15029 | Russell and Co. | Russel Office | 3300 South 2625 East | fireplace | 2 days
15030 | Kent Topham | Gregg Christensen | 2574 East Kentucky Ave | masonry wall | 3 weeks
15031 | Jaffa Group | Etlin | 2723 Estates Drive, Park Meadows | fireplaces | 1 week
15032 | Brad Reynolds | Hopkins | 5150 Holladay blvd | range hood | 2 days
15033 | Biltmore | Hinckley | Viewmont | Veneer | 6 weeks
15034 | Edge Builders | Burnett | 3905 E Park View, Olympus Cove | Veneer | 6 months
15035 | J&L | Ostler | 2428 N River Meadows pkwy, Midway | Veneer/bluestone | 3 months
15036 | Big D | Lindquist | Ogden | veneer | 4 days
15037 | GS Excel | Whalen | 3100 Meadows Drive, PC | veneer | 2 weeks
15038 | Big D | Forest Mcnab | 1880 East Shadow Valley Dr, Ogden | paving | 2 days
15039 | GS Excel | Lot 169 | 169, Colony | repairs | 3 weeks
15040 | RA Ferrin | Purcell | Deer Valley | fireplaces | 5 days
15041 | Allison Keele | Keele | 355 east 150 n Orem | fireplace | 1 day
15042 | GS Excel |  | 2702 Estates Drive, PC | repairs | 1 day
15043 | Dave Spafford | Dave Spafford | 2750 E Creek crossing | repairs | 3 days
15044 | Carol Wolfert | Carol Wolfert | 508 N. Country Manor Lane, Alpine | fireplce | 4 days
15045 | Edge Builders | Wasatch House | Olympus cove | paving | 2 months
15046 | J&L | Young | sugarhouse | paving | 5 weeks
15047 | Magleby Remodel | Thompson | Pepperwood | repairs | 2 days
15048 | Dolphin Pools | Brower | Bountiful | paving | 5 weeks
15049 | Russell and Co. | Waterman | Millcreek | veneer | 2 weeks
15050 | Steve Dubell | Ravi | 1600 Arlington Ave, SLC | fireplaces | 3 days
15051 | Hobble Creek Const | Huntsaker | Broken Spear, Tuhaye | repairs | 3 days
15052 | GS Excel | 169 Colony | 169 Colony | repairs | 2 weeks
15053 | Craig Const | Maxwell | 53 Colony, PC | landscaping
15054 | Big D | Juniper Extended Mirror | Victory Ranch 154 | veneer | 1 month
15055 | Big D | Aspen | Victory Ranch 148 | veneer | 1 month
15056 | Magleby Remodel | Reynolds | Promontory | fireplaces | 1 week
15057 | Norman | Landis | 33 Colony | repairs | 2 weeks
15058 | Top Mark Construction | Bridgewater | Wapiti Canyon, Promontory | veneer | 2 months
15059 | Magleby | Wadsworth | Pioneer Road, draper | veneer | 4 months
15060 | Big D | Cottonwood | Victory Ranch 160 | veneer | 1 month
15061 | Big D | Juniper | Victory Ranch 161 | veneer | 1 month
15062 | Big D | Juniper Extended | Victory Ranch 162 | veneer | 1 month
15063 | J&L | Brandon Leroy | Lehi | firerock,paving | 1 month
15064 | Magleby | Kirchheimer | Perserverance Court, Deer valley | veneer, paving | 1 month
15065 | RA Ferrin | Damron | Deer Valley | repairs | 3 days
15066 | GS Excel | 1978 Kidd circle | Park city | repairs | 1 day
15067 | Chamberlain | 6730 silver lake dr | Deer Valley | repairs | 2 days
15068 | Big D | Juniper Extended deck | Victory Ranch 123 | veneer | 1 month
15069 | Big D | Mirror Extended deck | Victory Ranch 131 | veneer | 2 month
15070 | Big D | Willow | Victory Ranch 133 | veneer | 3 month
15071 | Big D | Juniper Extended deck | Victory Ranch 134 | veneer | 4 month
15072 | Biltmore | Boyer | Viewmont | patios | 2 months
15073 | Russell and Co. | Waymant | 2636 E 6200 South | patios | 1 month
15074 | Chamberlain | Kirk | haven lane | repairs | 1 day
15075 | Magleby Remodel | Mendez | Alpine | repairs | 1 day
15076 | Shannow Wright | Nemeroff | Old Ranch road | veneer | 2 weeks
15077 | Norman | Silver Cloud | 2554 Silver Cloud crt | repairs | 1 day
10578

## 2014
Job # | Builder | Client's Name | Address | Description of work | Est. Time
14001 | Killowen | Lundahl | 250 West 600 South, Midway | Veneer | 2 weeks
14002 | Rochelle Warner Designs | Karen Morgan | 1537 Yale Avenue | fireplace | 1 day
14003 | Laura Hansen | Laura Hansen | Sandy | fireplace | 1 day
14004 | Jackson & Leroy | Burningham | 2917 Commanche | fireplace | 3 days
14005 | Eagle Mountain | Eagle Mountain HOA | Lehi | repairs | 3 days
14006 | Magleby | Wing | 180 North 1440 E, Springville | repairs | 1 week
14007 | GS Excel | Carrig | Salt Lake | repairs | 3 days
14008 | Craig Collins |  | 4870 South 2680 East, SLC | cmu walls | 3 days
14009 | RA Ferrin | 177 | Glenwild 177 | Veneer | 6 weeks
14010 | Steve Dubell | Johnson | 1015 (2950 s)Vista View Dr, SLC | fireplace | 1 day
14011 | Magleby | Mueller | Old Town Park City | Veneer | 3 montsh
14012 | Biltmore Company | Josh Romney | 2187 E 5340 S | fireplaces | 2 days
14013 | Jackson & Leroy | Steiner | Douglas St | window well | 3 days
14014 | Dave Spafford | Dave Spafford | 2750 E Creek Crossing Lane | repairs | 5 days
14015 | Greyhawk | Hamilton | 4528 Wander lane | Veneer | 6 weeks
14016 | Dolphin Pools | Wood | Alpine | pool coping | 1 week
14017 | Magleby | Robertson | Berkshires | Veneer | ?????
14018 | AMB Design | Trip | 3267 Big Spruce way | hearth | 2 hours
14019 | Hearth & Home |  | 3600 Constitution | Hearth | 2 days
14020 | Davies Development |  | Red Cloud, Deer Valley | hearth | 3 days
14021 | Seven Star Ranch | Ron Mika | 78 Wolf Creek | Fireplace, veneer | 6 weeks
14022 | Dave Freed | Dave Freed | Canyon Oak, SL | repairs | 3 days
14023 | Premier Restoration | Glenn | 500 South | veneer
14024 | Blake Roney | Blake Roney | Foothill Blvd, Provo | repairs | 4 days
14025 | Chamberlain Homes | Marquardt | Canyon Oak, SL | Veneer | 6 months
14026 |  | Simpson | 3740 Forest Hills Drive | patios, landscaping | 2 months
14027 | Jaffa Group | Miller | 3308 American Saddler Drive | fireplaces | 3 days
14028 | Colarusso Constructoin | Mendenhall barn | Alpine | Veneer | 1 week
14029 | Magleby | Christensen Repairs | Fayette | repairs | 1 day
14030 | Jackson & Leroy | Bagley | Salt Lake | repairs | 2 days
14031 | Jackson & Leroy | Hale |  | hearth and firebrick | 3 days
14032 | Biltmore Company | Mitt Romney | 2187 E 5320 S | Fireplace & landscape | 3 months
14033 | Chamberlain Homes | Mitt Romney | 6730 Silver Lake | repairs | 2 days
14034 | Jaffa Group | 172 Colony | 172 Colony | fireplace | 1 day
14035 | Patco Masonry | Wilson | 4073 Cumberland Drive. Holladay | landscaping | 2 months
14036 | Jackson & Leroy | Henderson | Parleys Terrace | veneer & landscape | 2 weeks
14037 | Picot Company | Hill | Cottonwood Lane | landscaping | 2 months
14038 | Picot Company | Broadbent | Hillsden Drive | landscaping | 1 month
14039 | Jackson & Leroy | Brown | Holladay | veneer | 3 weeks
14040 | Jackson & Leroy | James Huntsman | Military way, SL | treads and patio | 3 weeks
14041 | Kobalt Construction | Pugh | 2378 Cottonwood Lane | sample | 1 day
14042 | Jackson & Leroy | Steinmetz | Promontory | repairs | 1 day
14043 | Magleby Remodel | Nelleson | Mapleton | repairs | 1 day
14044 | Magleby Excavation |  | Cottonwood Lane | repar | 2 days
14045 | Lowell Construction | Moyle | Tomahawk Lane | tread | 1 day
14046 | Russel & Co |  | 2830 Little Valley, Wallsburg | veneer | 2 days
14047 | Jackson & Leroy | Kinney | 450 F St., SL | veneer | 3 weeks
14048 | Peak audio |  | 3 ravenwood, pepperwood | repairs | 1 day
14049 | Jackson & Leroy | Walker Lane Gate | Walker Lane, Holladay | entry gate | 1 week
14050 | Sunline Landscaping | Robertson | 1471 s 1140 e, orem | landscaping | 4 months
14051 | Hess Construction | Felton | 1156 Aerie Drive | veneer | 1 month
14052 | Hobble Creek Construction | Bullock | Colony 163, PC | veneer | 1 month
14053 | Tiffany Lemons | Lemons | 5049 N 400 W Old Ranch Rd, PC | landscaping | 2 months
14054 | Jackson & Leroy | Naisbitt | Gilroy circle, Olympus cove | veneer | 2 months
14055 | Jackson & Leroy | Ruud | Olympus cove | veneer | 2 months
14056 | Euclid Timber |  | Sundance | veneer | 3 days
14057 | Craig Construction | Gilmore | Lot 57, Colony | veneer | 4 months
14058 | Top Notch Construction | Parsons | 1607 S BasinView Road | veneer | 3 months

## 2013
Job # | Builder | Client's Name | Address | Description of work | Est. Time
13001 | Jackson & Leroy | Cohen | 5382 S 1830 E, holladay | fireplace | 2 days
13002 | Craig Construction | Jennings | Promontory | fireplace | 1 day
13003 | Jackson & Leroy | Tomlinson | Olympus Cove | repairs and veneer | 3 day
13004 | Hearth & Home | Central Bank | Provo | stone supply | 3 months
13005 | Anderson Consulting | Heath | Red Pine, Canyons, PC | veneer | 3 months
13006 | Lowell Construction | Stevens | Capitol | veneer | 2 months
13007 | Hacking Construction | Birritella | Sundance | veneer | 1 month
13008 | Peterson | Matt Peterson | Lindon | veneer | 1 week
13009 | Jackson & Leroy | Cavaletto | Draper | patio | 1 week
13010 | Jackson & Leroy | J&L Office | Holladay | repairs and patio | 2 weeks
13011 | Colcorp | Glenn | 3035 East 4409 South | veneer | 3 weeks
13012 | Henderson | Henderson | Winterton Circle | repairs | 1 day
13013 | Landform Design Group | Dee | 1575 Devonshire, SLC | veneer, cmu patios | 2 months
13014 | Dave Spafford | Dave Spafford | 2470 e creek crossing | repairs | 4 days
13015 | Big D | Cheryl | Cottonwood lane | repairs | 1 day
13016 | Craig Construction | Landis | 33 white pine | repairs | 2 days
13017 | Craig Construction | Mendelson | 60 west hills, promontory | veneer | 2 months
13018 | Kappus | Glief | SLC | stone supply | 2 days
13019 | Chamberlain | Durham | Holliday Blvd, | repairs | 1 week
13020 | GS Excel | Stag 48 | Stag Lodge 48, Deer Valley | veneer | 1 week
13021 | RA Ferrin | Sherry | 91 Glenwild, PC | veneer | 2 months
13022 | Magleby | Silver Lake Model Home | Park City | veneer | 2 months
13023 | Hearth & Home | ICO: The District | 11200 South Bangerter | architectural | 3 days
13024 | Eagle Mountain HOA | HOA | Eagle mountain | cmu | 2 days
13025 | Ken Kirkham | Lemetrie | 2500 White Pine, PC | patio | 3 weeks
13026 | Magleby | Silver Lake Entry Gate | Park City | veneer | 2 weeks
13027 | Keller Development | Larsson | Holladay | fireplace fabrication | 3 weeks
13028 | Magleby Remodel | Nelleson | 542 South Eagle, Mapleton | repairs | 1 day
13029 | Lowell Construction |  | 101 Sugarplum, Snowbird | repairs | 3 days
13030 | Jackson & Leroy | Allison | 4350 South 2900 East | veneer | 2 wk
13031 | RA Ferrin | Morning Star | Morningstar Drive, Park City | repairs | 3 days
13032 | Jackson & Leroy | Barth | Wilshire Drive, SL | fireplace | 2 days
13033 | Jackson & Leroy | Huntsman | Brentwood Drive, SL | fireplaces, etc | 2 months
13034 | RA Ferrin | Vintage Tunnel | Vintage, Canyons | veneer | 1 month
13035 | AMB Design | Meadowlark | Center Creek | fireplaces, etc | 2 weeks
13036 | AMB Design | Clark |  | fireplaces | 3 days
13037 | AMB Design | Nantz | San Diego | fireplace | no install
13038 | Hearth & Home | Cosgrove | Draper | architectural | 2 months
13039 | Craig Construction | Edwards | 39, promontory | fireplaces | 3 days
13040 | JLR | Nicole | 1046 West Pheasant Tail | fireplace | 1 day
13041 | Hobble Creek Const | Minshew | 599 W 2925 S, Mapleton | veneer | 6 weeks
13042 | Jackson & Leroy | Hansen | 6200 South, Holladay | veneer | 6 months
13043
13067 | Magleby | Gardiner | 67 Wolf Creek | veneer | 6 months

## 2012
Job # | Builder | Client's Name | Address | Description of work | Est. Time
12001 | Jackson & Leroy | Bowen | 2480 East Walker Lane, Holladay | Demolition, Bluestone | 8 months
12002 | Richard Picot | Dave Weiss | 9726 Ruskin Ct. | repair | 1 day
12003 | Jackson & Leroy | Bonnie | Quail Hollow | demolition, stone veneer | 1 month
12004 | Jackson & Leroy | Madsen | 2828 Kennedy Drive, SL | repair | 3 days
12005 | Michelle Hyde | Nate and Michelle Hyde | Alpine | fireplace | 3 days
12006 | Ann Marie Barton | Radman | Wander Ln. | fireplace | 3 days
12007 | Mark Miller | Mark Miller | Carrigan Canyon | repairs | 1 week
12008 | Dave Spafford | Dave Spafford | 2750 Creek Canyon Lane | repairs | 1 week
12009 | Miller Construction | Riverside CC | Riverside Country Club | Veneer | 1 month
12010 | Magleby Companies | Garret Devore | Provo Canyon | Veneer | 1 year
12011 | Lowell Construction | Glei | Salt Lake | steps | 1 day
12012 | Magleby Companies | Gulley | Deer Crest | repairs | 6 weeks
12013 | Jackson & Leroy | Pynes | 2304 Berkeley | patios | 3 weeks
12014 | Chamberlain Homes | Schebler | Coalition Court, Deer Valley | patios | 1 week
12015 | Picot Landscaping | Marsden | Salt Lake | patios | 2 weeks
12016 | Hotel Park City | Guy Morris | Park City | repairs | 1 day
12017 | Michael Fairclough | Michael Fairclough | Tate Lane, Midway | repairs | 1 day
12018 | Majestic Stone | Majestic Stone | 300 West, SLC | fireplace | 1 day
12019 | RA Ferrin | Ferrin | 168 Glenwild | Veneer | 1 month
12020 | Magleby Companies | Stapley | Sundance | repairs and veneer | 1 month
12021 | Jen Tayler | Ingram | 9468 N 6560 W, Highland | fireplace | 2 weeks
12022 | Magleby Companies | Duff Thompson | Sundance | repairs | 1 day
12023 | GS Excel | Babcock | Weber Canyon, Oakley | Veneer | 1 month
12024 | GS Excel | Dunn | Stag Lodge 47, Deer Valley | Veneer | 1 month
12025 | Big D | Huntsman BBQ | Cottonwood land, Holladay | BBQ | 1 week
12026 | Ann Marie Barton | Nantz | Pepple beach, CA | Limestone work | 2 weeks
12027 | Boyer | Sara Boyer | Crestview Cir | repairs | 3 days
12028 | Andersoning consulting | Todd Pedersen | Orem | repairs | 2 days
12029 | RA Ferrin | Ferrin's old home | Haven Lane | demo and fireplace | 2 days
12030 | Barbara Catron | Catron | 13118 S 1300 w riverton | monument | 2 days
12031 | Darin | Darin's neighbor | midway | bench, firepit | 1 week
12032 | Magleby Companies | Sam Dominguez | Highland | repairs | 1 day
12033 | Dolphin Pools | Red Butte Gardens | Wakara Lane, U of U | repairs | 1 day
12034 | Coelho Construction | Coehlo | Marmot Circle, Promontory | repairs | 2 days
12035 | Magleby Companies | Ron Mika | Lot 77 wolfcreek | Fire pit and garage
12036 | Spencer Eccles | Spencer Eccles | Park View Lane, Olympus Cove | repairs | 2 days
12037 | Magleby Companies | Colorusso Stairs | Harvard Lande, SLC | Veneer | 6 weeks
12038 | BMA | Ashton cabin | Sundance | repairs | 1.5 days
12039 | Magleby Companies | Maui Chai | Orem | brick, precast, fireplaces | 2 months
12040 | Dolphin Pools | Rich Kay | North Cove, salt lake | bluestone, landscaping | 3 weeks
12041 | Jackson & Leroy | Dunkin | 99 West Promontory Tower, SLC | fireplace | 1 day
12042 | Craig Construction | Hopkins | Lot 42 Deer Crossing Promontory | fireplaces | 4 days
12043 | Magleby Companies | Dr. Oh | Lot 43, Wolf Creek | CMU, Veneer | 6 months
12044 | Hearth & Home | Rock Canyon Bank | Rock Canyon, Provo | stone supply | 2 months
12045 | Magleby Companies | Chris Thompson | lot 6 Snow Forest, Pepperwood | repairs | 2 weeks
12046 | AMB Design | Wilmarth | Wander Ln. | fireplace | 2 days
12047 | Steve Schow | Silver Strike Lodge | Silver strike lodge | repairs | 1 day
12048 | Jackson & Leroy | Topham | Holladay | Veneer | 4 weeks
12049 | Dolphin Pools | Hartman | Sandy | repairs | 1 day
12050 | Robyn Kremer | Kremer | 2033 Ridgehill, Bountiful | Veneer | 2 weeks
12051 | Roxbury Studios | Vallejo | Alpine | Fireplace | 1 week
12052 | Magleby Companies | Gunther | 860 East 700 N, american fork | repairs | 2 days
12053 | Magleby Companies | Christensen Garage | Fayette | Veneer | 1 month
12054 | Magleby Companies | Switzler | Hidden Oaks, Highland | Veneer | 3 months
12055 | Templetes | Knudsen | 65 thaynes canyon, PC | fireplace | 1 week
12056 | Meridian | Capital Oak HOA | Capital Oak, SLC | plaques | 1 day
12057 | AMB Design | White | 6115 Old Orchard Lane | fireplace | 3 days

## 2011
Artistic Stone Masonry - 2011 Job List
Job # | Builder | Client's Name | Address | Description of work | Est. Time
11001 | Magleby Companies | Legacy | 13115 South 1300 West, Riverton | Stone and flooring | 2 months
11002 | Magleby Companies | Riverside Country Club | University Avenue, Provo | Repairs | 2 days
11003 | A2Z Management | Summer Raazz | Lehi | Firerock | 3 days
11004 | Jackson & Leroy | Ostler | Salt Lake | Veneer | 2 weeks
11005 | Doug Knight | Gordan Smith | Glenwild #5 | fireplaces | 2 months
11006 | Dolphin Pools | Freidlander | Brentwood | Pool coping | 4 Days
11007 | Dave Spafford | Dave Spafford | 2750 East Creek Crossing Lane | Repairs | 2 weeks
11008 | Craig Construction | Browning | 3415 Meadows Drive, Park City | fireplaces | 2 weeks
11009 | BMA Construction | Ashton | Sundance | Repairs | 2 days
11010 | Ochsenhirt | Nate Ochsenhirt | 3600 Professional Park, Lehi | CMU | 3 days
11011 | Magleby Companies | Marsh | 1664 Stoneridge Dr, Bountiful | Fireplace and veneer | 3 months
11012 | Magleby Companies | Weidman | Stonegate, Provo | Fire Rock and veneer | 2 months
11013 | Magleby Companies | Evans | Peppertree, Sandy | Veneer | 4 months
11014 | Spencer Eccles | Spencer Eccles | Park View Dr. Olympus Cove | Repairs | 4 Days
11015 | TAC Construction | Rick Burnham | Wolf Creek 75 | Repairs | 3 days
11016 | Saddle Ridge HOA | Dennis Ralph | HOA | Landscaping | 3 days
11017 |  |  | Stonegate, Provo | Repairs | 3 hours
11018 | Anderson Consulting | Pollack | Sundance | Veneer | 1 month
11019 | Keller Development | Pederson | Holladay Blvd, Holladay | fireplaces & landscaping | 2 months
11020 | Chamberlain Homes | Parkin | Salt Lake | Veneer | 1 week
11021 | Mitzi Krantz | Krantz | Olympus Cove | fireplace | 3 days
11022 | GS Excel | Freed | North Cove | Repairs | 1 day
11023 | Anderson Consulting | Dr. Girstman | Sundance | Repairs | 1 day
11024 | Magleby Companies | Praetor Pavillon | Wyoming | Veneer | 2 weeks
11025 | RA Ferrin | Wooded Cove | 5340 South 2200 East | brick | 1 week
11026 | Dolphin Pools | Dolphin Pools Showroom | Highland Drive | Pool coping | 2 days
11027 | Magleby Companies | James remodel | Alpine | Repairs | 2 days
11028 | Diamond Phillips | Randall Bridge | Fort Douglas, SLC | Paving | 1 week
11029 | Distinctive Designs | Dupont | 3077 Ksel Drive, Sandy | Granite cap | 1 day
11030 | Magleby Companies | Greenwald | Promontory | Veneer | 2 months
11031 | Craig Construction | Fisher | Colony 46 | Repairs | 1 day
11032 |  | Lot 100 | Lot 100 Colony | Repairs | 1 day
11033 | Skyway Construction | Thorpe Poolhouse | Berkshires | Veneer | 1 week
11034 | Talisker Development | Talisker HOA | Empire Pass | Repairs | 2 weeks
11035 | Midway Construction | Girardin | Deer Crest 99 | fireplace | 1 week
11036 | Craig Construction | Gabriel | 135 Colony | Repairs | 3 days
11037 | Magleby Companies | Brunn | 1192 S Carterville Road | Repairs | 2 hours
11038 | Dave Wathen | Ward | 6104 Lewis and Clark | Veneer | 4 weeks
11039 | Magleby Companies | Olsen | Alpine | Repairs | 4 weeks
11040 | Magleby Companies | Mendenhall/Alpine Ranch | Alpine | Veneer | 6 weeks
11041 | Suzie Turner | Suzie Turner | Provo | fireplace | 2 days
11042 | Chamberlain Homes | Schebler | Coalition court | Veneer | 4 Days
11043 | Magleby Companies | Oh | lot 43 Wolf Creek | Veneer | 2 weeks
11044 | Jackson & Leroy | 4460 Adonis | 4460 Adonis | Repairs | 1/2 day
11045 | Jackson & Leroy | Hicks | 4000 south & alveira | Repairs | 1/2 day
11046 | Colcorp | Glenn | 4409 south 3035 east | Veneer | 2 days
11047 | Anderson Consulting | repairs | Sundance | Repairs | 1 day

## 2008
Artistic Stone Masonry - 2008 Job List
Job # | Builder | Client | Address | Description of Work | Est. Time
8001 | Chamberlain Homes | Tempest | Marilyn St, Holladay | veneer | 2 months
8002 | Lowell Construction | Soinski | Walker Lane, Holladay | pre-cast caps | 2 days
8003 | Magleby Companies | Darly Magleby | Lindon | sills | 2 days
8004 | Magleby Companies | Mills | Lot 57 Wolf Creek | veneer | 2 months
8005 | Hess Construction | Nader | Lot 10 Wolf Creek | fireplace | 1.5 weeks
8006 | C&C Landscaping | Home Show Daily | 300 West 1700 South | veneer | 1 week
8007 | C&C Landscaping | Home & Garden Sho | Sandy Expo Center | fireplace | 1 week
8008 | C&C Landscaping | Richards |  | landscaping | 2 weeks
8009 | Magleby Companies | Woods | Alpine | veneer | 3 months
8010 | C&C Landscaping | Adams | Highland | landscaping | 1 week
8011 | Daley Landscaping | Daley | Springville | fireplace | 3 days
8012 | Hardy Companies | Hardy | Lot 31 Dutch Fields, Midway | veneer | 2 months
8013 | Jackson & Leroy | Bazail | Douglas St, SLC | veneer | 1.5 months
8014 | Craig Construction | Timbrook | Lot 176 Colony | veneer | 6 months
8015 | Craig Construction | Sullivan | Lot 168 Colony | veneer | 6 months
8016 | Magleby Companies | Red Ledges | 2400 E Center, Heber | CMU, veneer | 1.5 weeks
8017 | GS Excel | Petersen | Atkin Ave | veneer | 2 months
8018 | Masterpiece Builders | Brand | 2490 Walker Lane | 4 FireRocks | 1 week
8019 | Daley Landscaping |  | 3540 N 400 W, Provo | landscaping | 1 week
8020 | Dolphin Pools | Sorenson | Murray UT | Pool Coping | 1 week
8021 | C&C Landscaping | Lynn | Moffet Lane, Holladay | landscaping | 2 weeks
8022 | Dave Spafford | Dave Spafford | 2750 Creek Crossing Lane | repairs | 2 weeks
8023 | Magleby Companies | Loveland | High Ridge Lane | veneer | 4 months
8024 | Chris Williams | Chris Williams | Lot 40 Tuhaye | veneer | 2 months
8025 | Picot Landscaping | Cory Brand | Havenwood Lan, Holladay | landscaping | 1 month
8026 | Heather Hoffman | Heather Hoffman | Holladay | fireplace | 2 days
8027 | Glen Hughes | Glen Hughes | Farmington | fireplace | 2 days
8028 | AMB Design | Albouy | Walker Lane, Holladay | veneer
8029 | Artistic Stone | Dennis Ralph | Eagle Mountain | veneer
8030 | Hacking Construction | Birrittella | Deer Run, Sundance | landscaping | 2 weeks
8031 | Artistic Stone | Darin Ralph | 280 W. 500 S. Midway | veneer
8032 | Stu Brisch | Stu Brisch | Olympus Cove | repairs | 1 day
8033 | Big D | Hawks | Hunstville | veneer | 18 months
8034 | GS Excel | Eccles | Park View DR, Olympus | repairs | 1 day
8035 | Craig Construction | Roney Addition | Deer Valley | veneer | 1 month
8036 | Craig Construction | Baker | 31 Glenwild, Park City | patio | 1 week
8037 | Craig Collins Const. | Simon McInnis | Walker Lane, Holladay | patio | 1 week
8038 | Distinctive Designs | Garff Ranch | Peoa Canyon | patio | 1 day
8039 | RA Ferrin | Lot 5 | Lot 5 Vinatge, Park City | veneer | 2 months
8040 | Craig Construction | Gabriel | Lot 135, Colony | veneer | 4 months
8041 | Craig Construction | Potter | Lot 30 Colony | chimney caps | 2 weeks
8042 | Craig Construction | McGrath | Lot 37, Colony | landscaping | 2 weeks
8043 | Timberridge Homes | Fairclough | Tate Lane, Midway | veneer | 2 months
8044 | AMB Design | Holladay Gardens | Holiday Road, Holladay | door surround | 2 days
8045 | Chamberlain Homes | Durham | Holiday Road, Holladay | patio | 1 week
8046 | Magleby Companies | Carlson | Pinebrook, Park City | patio | 2 wk
8047 | McCarthey Homes | Deer Crest | Deer Crest, Park City | fire Rock and veneer | 2 months
8048 | Dave Wathen | LDS Church | Spanish Fork | demolition | 1 day
8049 | Magleby Companies | Roney Repairs | Deer Valley | demolition, repairs | 2 weeks
8050 | Chamberlain Homes | Checketts | Lot 12, Wolf Creek Ranches | veneer | 6 weeks
8051 | Custom Scandinavian | Priestly | Lot 71, Promontory | fireplace | 3 days
8052 | Magleby Companies | Aspen Camp 84 | Aspen Camp, Promontory | landscaping | 1 week
8053 | Distinctive Designs | Plum Tree | 905 S 505 E, North Salt Lake | landscaping | 1 week
8054 | Magleby Companies | Savage | Lot 148, Colony | veneer | 4 months
8055 | Magleby Companies | Bullock | Highland | veneer | 1 month
8056 | Wathen | Ogden | Downtown, SLC | fireplace | 2 days
8057 | RA Ferrin | Lot 8 | Lot 8 Vintage, Park City | veneer | 2 months
8058 | Robin Goodfellow | Cook | Holladay | veneer | 1 month
8059 | Lowell Construction | Petersen | Holladay | veneer | 1 month
8060 | Lowell Construction | Kemp | Glenwild lot 12, Park City | veneer | 4 months
8061 | Magleby Companies | Minton | Sundance | landscaping | 1 week
8062 | Magleby Companies | Nydeggar | Highland | repairs | 1 day
8063 | Hacking Construction | Sundance | Sundance | repairs | 1 day
8064 | GS Excel | Stag 47 | Deer Valley | repairs | 2 days
8065 | Jackson & Leroy | Jackson | Salt Lake | veneer | 1 month
8066 | D Constructors |  | Avenues | landscaping | 2 weeks
8077 | Magleby Companies | Mika Main House | Lot 77 Wolf Creek Ranches | veneer | 6 months

## 2009
Artistic Stone Masonry - 2009 Job List
Job # | Builder | Client | Address | Description of Work | Est. Time
9002 | Magleby Companies | Christensen | Fayette | Veneer | 4 months
9079 | Magleby Companies | Barker | Wolf Creek, Lot 79 | Veneer | 5 months
9003 | AMB Design | Rigby |  | Hearth stone | 1 day
9004 | AMB Design | Barton | Kelly Circle | Interior Flooring | 1 week
9057 | Chamberlain Homes | Pehrson | Wolf Creek, Lot 57 | Veneer | 4 months
9005 | Chamberlain Homes | Spencer Kirk | Haven Lane, Holladay | Veneer
9006 | Jesse Carr | Sundance | Sundance | sinks | 1 day
9013 | LLL Homebuilders | Dawson | Lot 13, Tuhaye | fire rock | 2 days
9009 | RA Ferrin | RA Ferrin | Canyons Lot #9 | Veneer
9015 | RA Ferrin | RA Ferrin | Canyons Lot #15 | fireplaces | 1 week
9531 | Big D | Haycock | 9531 North Salt Lake | landscaping wall | 1 week
9853 | Chamberlain Homes | Mitt Romney | 9853 Rising Star, Park City | repairs | 1 day
9105 | Hess Construction | Marshall | Lot 5 Glenwild, Park City | fireplaces | 2 days
9338 | Picot Landscaping | Zebrack | 1338 Alta St. SLC | exterior patios | 3 weeks
92464 | Jackson & Leroy | Jeremy Jackson | 2646 E Arnett Dr. | fireplaces | 3 day
92750 | Spafford | Dave Spafford | 2750 E Holladay Blvd | repairs | 3 day
9563 | Picot Landscaping | Alex Bocock | 563 N Perry's Hollow | landscaping wall | 1 week
9010 | Hearth & Home | Staybridge Hotel | West Valley | firerock | 3 days
9011 | Hotel Park City | Hotel Park City | 2001 Park Avenue | repairs | 1 day
9012 | Magleby Companies | Eric Magleby Repairs | Golden Eagle Circle, Alpine | repairs | 1 day
9014 | Lowell Construction | Judy Moyle Repairs | Tomahawk | repairs | 3 days
9016 | William Schmingle | Holcomb | Royal Lane, Cottonwood | Veneer | 3 months
9017 | Jerry Andersen | Pedersen | Orem | landscaping wall | 1 month
9018 | RA Ferrin | Warr | Salt Lake | interiors | 1 week
9019 | Magleby Companies | BeeBe | Interlakken, Midway | Veneer | 1 month
9020 | Butterfield | Vicky Butterfield | Ephraim | Veneer | 1 month
9021 | GS Excel | Orlowski | Telemark Dr, Deer Valley | repairs | 2 days
9022 | McCarthey Homes | Deer Crest | Deer Crest, Deer Valley | firerock | 1 week
9023 | Ivory Homes | Clark Ivory | Millcreek | flooring | 1 week
9024 | Craig Construction | Neske | Deer Valley, Lot 74 | repairs | 2 days
9025 | Big D | Weinman | 3853 Rockport Ridge, Promontory | Veneer | 6 months
9026 | Jackson & Leroy | Bea | Brighton | Veneer | 2 months
9027 | Lowell Construction | Egan | 2950 East Lake Merry, Sandy | landscaping wall | 1 week
9028 | Ivory Homes | Jennifer Romney | 1805 East Millbrook | patio | 1 week
9029 | Talisker Group | Talisker | Empire Pass | repairs | 1 week
9428 | Centerpointe | Brand | 428 Ontario, Deer Valley | fireplaces | 2 weeks
96005 | Jackson & Leroy | Pingree | 6005 Holladay BLvd, | Veneer | 6 months
9030 | Talisker Group | Black rock | Park City | Veneer | 1 week
9083 | Jackson & Leroy | Steinmetz | Lot 83 Promontory | demolition and Veneer | 1 month
9036 | Tuck Landscaping | Glenwild 36 | Glenwild 36 | Veneer | 1 month
9113 | Magleby Companies | Vance | Wolf Creek 13 | Veneer | 3 months
9250 | Midway Construction | Hills | 250 West Midway | Veneer | 2 weeks
9031 | Tracy Mackey | Tracy Mackey | personal project | materials
9040 | Magleby Companies | Christensen Remodel | Fayette | Veneer | 2 weeks
9041 | Tricon Builders | Soo Chung | 9110 North Uintah, Tuhaye | firebrick | 1 day
9087 | Craig Construction | Strasser | Lot 87 Colony | Veneer | 2 weeks
9042 | Jon Moe | Jon Moe | Sundance | fireplaces | 2 days
9043 | R&O Construction | Redford Convention Ctr | Sundance | supply | 1 day

## 2010
Artistic Stone Masonry - 2010 Job List
Job # | Builder | Client's Name | Address | Description of work | Est. Time
10001 | Lowell Construction | Rhode | South Temple | Stone, CMU, Demolition | 2 months
10089 | Craig Construction | Flatley | 89 Silver Strike, Deer Valley | Fire Rock | 2 weeks
10108 | Craig Construction | Archibald | Lot 108 Colony, Park City | Fire Rock and Stone Veneer | 3 months
10002 | Craig Construction | Binder | Promontory, Park City | Fire Rock | 1 week
10003 | AMB Design | Watson Tennesee | Memphis Tennessee | Stone Mantle fabrication | n/a
10018 | RA Ferrin | Unit 18 | Canyons | Stone Mantle fabrication | 1 day
11595 | Magleby Companies | Warner | 1595 West 1100 North, Provo | Stone Veneer | 1 week
10004 | Magleby Companies | Roney | Foothill Blvd, Provo | Repairs | 2 days
10005 | Magleby Companies | Riverside Country Club | University Avenue, Provo | Stone Veneer | 4 Months
11417 | AMB Design | Barton | 1417 Kelly Circle, Holladay | Flooring | 3 weeks
14223 | Magleby Companies | James | 4223 Vintage Circle, Provo | Landscaping wall | 1 week
12701 | Miller Construction | Caesars Palace | 2701 N University Avenue, Provo | Stone Veneer | 1 week
11971 | Magleby Companies | Wyatt Remodel | Deer Valley | Repairs | 2 days
10006 | Bud Bailey | Baily Repairs | Salt Lake | Repairs | 1 day
10007 | RA Ferrin | Manny | 2706 Ridge Hill Road, Bountiful | Repairs | 3 days
10008 | Hotel Park City | Hotel Park City | Park City | Repairs | 2 days
10163 | Mark Campbell Const | Bullock | 163 Colony | Repairs | 6 days
10009 | Magleby Companies | Carter | Old Ranch Road, Park City | Repairs | 2 days
10010 | Picot Landscaping |  | 4281 Abinadi, Olympus Cove | Landscaping wall | 4 days
10011 | AMB Design | Layton | 2421 E Walker Lane | fireplaces | 2 days
10012 | Babcock | Christain Gardner | Crestview | Flooring | 5 days
10013 | Varela | Varela | Ogden | fireplaces | 1 day
10014 | Magleby Companies | Asay Repairs | Vivian Park, Provo | Repairs | 1 day
10015 | Dennis Ralph | HOA Sign |  | signage | 2 days
10016 | Lowell Construction | Gardner | 1529 Arlington, SLC | pavers | 1 week
10017 | Andersen Consulting | Asay Repairs | 3512 Orem | Repairs | 1 day
10018 | Roundy Masonry | Glendale WY | Glendale WY | firerock | 2 days
10019 | Magleby Companies | Roberts | Promontory, Park City | veneer | 6 weeks
10020 | Magleby Companies | Roney Cabin | Sundance | veneer | 4 weeks
10021 | Brad Smith | Stock | Maple Ridge Subdivision | veneer | 10 weeks
10022 | AMB Design | Kelly Scott | Draper | fireplaces | 3 days
10023 | Picot Landscaping | Marsden | 2460 East 900 South | Flooring | 1 week
10024 | Lowell Construction | Stewart | A Street, SLC | Repairs | 1 day
10656 | Andersen Consulting |  | 656 Coalition ct, Deer Valley | repairs | 2 days
10025 | Andersen Consulting | Dallin | Sundance | Repairs | 1 day
10026 | RA Ferrin | Hulme | Coalition Court, Deer Valley | veneer | 3 weeks
12750 | Dave Spafford | Spafford | 2750 East Creek Crossing | Landscaping wall | 2 weeks
12500 | Chamberlain Homes | Lemaitre | 2500 West White Pine Canyon | veneer | 2 months
14033 | Jackson & leroy | Jacobs | 4033 Prospector | Landscaping wall | 2 weeks
10027 | Lowell Construction | Spear | Bear Hollow | Repairs | 3 days
10935 | Jill Olson | Olson | 933 Hubbard ave | Flooring | 2 days
12379 | AMB Design | Rigby Mantle | 2379 Shadowood, Holladay | fireplaces | 2 days
10600 | Magleby Companies | Peterson | 94 West 600 North, Lindon | veneer | 2 months
10028 | AMB Design | White | Monte Luca Drive | fireplaces | 1.5 weeks
10029 | Hacking Construction | Sundance repairs | sundance Drive | Repairs | 3 days
10030 | Chamberlain Homes | Marty | 5841 Falcon Court, Deer Valley | Repairs | 2 days